## Sheet1
Task
Inception and Elaboration |  |  | CLOSED
Construction
Construction Alpha1
|  | Deploy to QA | 2/2/09
|  | Deploy to Stage | 2/18/09
Construction Alpha2
|  | Deploy to QA | 3/5/09
|  | Deploy to Stage | 3/24/09
Construction RC1
|  | Deploy to QA | 4/6/09
|  | Deploy to Stage | 4/23/09
Construction RC2
|  | Deploy to QA | 4/22/09
|  | Deploy to Stage | 5/15/09
Construction RC3
|  | Deploy to QA | 5/8/09
|  | Deploy to Stage | 6/4/09
Transition
| Deploy to PROD |  | 6/24