## Risks
ID | Risk | Description | Owner | Impact | Mitigation Plan | Priority | Status | Comments/Resolution
R1 | Short-term solution for the TCGA large data set support was added late to the caArray scope. | The short-term solution to the TCGA data load problem was added late and has impacted the schedule. | Nobody | Medium |  | Medium | Closed | After evaluation and final solution of the data load problem, the schedule for caArray releases has been moved out to accommodate this extra requirement.
R2 | Developer for caIntegrator coming on board late | The second developer for caIntegrator will come on board on October 1 instead of on September 1, 2011 | Rashmi Srinivasa | Medium |  | Medium | Closed | An experienced caBIG developer is on board October 1.
R3 | BDA-Lite requirements adds to scope | The enterprise-mandated BDA-Lite requirement has added to the scope of both caArray and caIntegrator and has impacted the schedule. | JJ Pan | High | Discuss timeline and support from Systems team. | High | Open | The schedule has been extended to accommodate these extra requirements. BDALite has now been implemented on the DEV and QA tiers, but not on STAGE and PRODUCTION yet.
R4 | New CIT policy re: Medium vulnerabilities | The new CIT security policy of mandating resolution of Medium vulnerabilities from app scans will impact the schedule of upcoming releases for caArray and caIntegrator. | JJ Pan | High | Discuss timeline from Systems team. Schedule early preparatory app scans to discover problems earlier. | High | Closed | caArray 2.4.1 and caIntegrator 1.3 addressed these new requirements and were successfully released.
R5 | Significant maintenance and engineering work affect feature development in SOW | Both the caArray and caIntegrator teams are putting a significant amount of effort towards maintenance and engineering activities (like 508 compliance, security issues, tech stack upgrades) now. These are important activities, but they were not listed specifically and may have an impact on the deliverables for the other features listed on SOW | Juli Klemm and Mervi Heiskanen | High | Prioritize requirements with Juli, Mervi and JJ. | High | Closed | The caArray and caIntegrator project plans were adjusted to account for these priorities, and project plan walthroughs were completed in January 2012.
R6 | Retirement of old Ivy and Gforge repositories will result in users being unable to build from source code of older versions of caArray and caIntegrator. | The current release under development (e.g., caArray 2.5.0) has been updated (along with the BDA version it uses - 1.7) to refer to the new repositories. However, older versions (e.g., caArray 2.4.1, 2.4.0. 2.3.1.1, etc.) have not been upgraded in this way. This means that if a user tries to build these older versions from source code, the build will fail. | JJ Pan, Juli Klemm and Mervi Heiskanen | High | Ask the Systems team to resurrect the old Ivy/Gforge repositories in a read-only mode for a few months. | High | Open | The alternatives and LOEs have been communicated to NCI and SAIC-F, and we are awaiting a decision on which course of action to take.
R7 | No support for BDA | Many applications (including caArray and caIntegrator) rely on the BDA jars to do build, deploy and artifact-generation/configuration (e.g., installers/upgraders). With the move to BDALite, several build modifications have been made, and the BDA code has been patched to work with the new NCI/Nexus repositories. However, there is a risk remaining in that these applications still depend on the patched BDA code, and there is no team at the NCI to support that code any more. The best solution would be to rewrite the build and deploy scripts for these applications from scratch, removing all reliance on the BDA code, but this will be time-consuming. | JJ Pan, Juli Klemm and Mervi Heiskanen | High |  | High | Open | The risk has been communicated to the NCI, and the current decision is to continue with the reliance on the patched BDA code.
R8 | TRANSCEND architecture decisions will affect scope significantly |  | JJ Pan | High |  |  |  | We are awaiting the final decision on architecture from the ESSRT team and can plan TRANSCEND features only after this.
R9 | Coordinated release of caArray, caIntegrator and UPT is needed for tech stack consistency. |  | Rashmi and Shine | Medium |  | Medium | Open | The dependencies among teams is a risk to the schedule of each individual project.