## 250_Plan_Pass2
Integration/caBIG
29168 | Talk to CTRP/PODS teams and NCI/CBIIT to figure out a plan for Grid security implementation.
Upload/Download/Import
29167 | Implement cloud storage of raw data files and allow local installers to configure storage.
29034 | Upload/download manager: resumable downloads, transparent compression
29164 | Prototype parsed data storage on the file system (NetCDF). Figure out how to transition the cancer centers' data. Test performance / transaction limits.
29036 | Investigate and prototype Postgres to get around database size/performance limits
13114 | Add ability to see position of imports in Queue and perhaps managing the queue
29166 | Allow unparsed import of fastq, SAM and BAM files from next gen sequencing experiments.
29165 | Support Assay Type and Technology Type columns in the SDRF as defined in MAGE-TAB spec v1.1.
Users/Collaborators
14630 | A collaborator who uploads files cannot see their own files in the manage data tab
26310 | Design a new UI for assigning permissions to samples | Review UI and see if we should implement in 2.5.0
Curation/Quality
13164 | Limit organisms to NCBI taxonomy term source only
29399 | Write an upgrade script that will clean up duplicate organisms in the database to limit them to the NCBI taxonomy term source.
14023 | Limit Material Type and Protocol Type terms to the MGED Ontologies | Same as above
29400 | Write an upgrade script that will clean up duplicate material types and protocol types in the database to limit them to the MGED ontology term source.
? | Remove Term Source version from the model | Talk to Juli & enter new issue
Search/Browse
22635 | Support searches for Experiment by Publication (by pubmed id and PI)
25128 | Search for and download Samples within an Experiment
20727 | Usability Enhancement: Add a button to "Show All" on all tabs under Annotation (could lead to slow page loads)
Misc
26303 | Upgrade to JBoss 5.1, except for upgrading from a previous installation
26304 | Implement support for JBoss 5.1 in the upgrade installers
26305 | Upgrade to Java 6
16610 | Support API access by Java 1.6 clients
29074 | Update documentation to reflect MySQL version 5.1
18758 | Support caArray Grid Service in JBOSS 4.0.5
10479 | Coverage > 80/70
21127 | Fix resetting of database state for integration tests
22546 | The add new Source/Sample/Extract/Labeled Extract/Hybridization GUI is broken in IE 8.
19044 | Need to add single-command-build and single command-deployment support to caArray build for BDA certification compliance. |  | Bill will talk to Anand about BDA compliance; partially resolved
18732 | Implement section 508 compliance (Reduction of issues by 30%) |  | Need to get 508 report run
28935 | Fix implementations of equals() and hashCode() for entities
29207 | Reduce CI build time to 15 minutes.
29208 | Improve build time on CI machine to match local times.
29170 | Unexpected error while deleting hybridization

## 250_Plan_Pass_1
Integration/caBIG
| Grid Security | Talk to Braulio Cabral: explain our planned approach to him, find out if he can recommend an incremental approach / how should we plan our security roadmap. Can include implementation of some of the following items.
15168 | Grid security: Implement grid authentication in remote java API
19782 | Grid security: Set up build/installer infrastructure needed for secure grid services
19783 | Grid security: Integrate CGMM
20302 | Grid security: Implement bulk-migration of CSM to Grid accounts if those accounts are on a known LDAP server that will be grid enabled
caTissue integration
29076 | Do requirements specification for integration with biospecimen systems like caTissue | caTissue contract is just kicking off: find out what services they are creating, and how we coordinate with their team. Do Requirements specification in 2.5.0. Implementation items that may come out of this effort are 29045, 29046, 17118 and possibly others.
Writable API
29044 | Writable APIs to create expt, upload and import data
Plugin parsers
28258 | Implement plugin architecture for platform parsers | Need to coordinate with caInt2, geWorkbench & GenePattern teams
Upload/Download/Import
| Eliminate need to chunk large data sets for upload and import | Investigate solutions and come up with a roadmap. Solutions could include some of the following.
12119 | Allow files greater than 1 GB to be uploaded | Consider allowing tar.gz uploads and HTML 5
29034 | Upload/download manager: resumable downloads, transparent compression
17430 | Split up import jobs into multiple transactions | This has the advantage of allowing for concurrent imports as well.
13114 | Add ability to see position of imports in Queue and perhaps managing the queue
| Ability to deal with many terabytes of data. (Already a problem as TCGA has ramped up.) | Investigate solutions and come up with a roadmap. Solutions could include some of the following.
29047 | Investigate storing files on the file system instead of the database.
29036 | Investigate Postgres to get around database size/performance limits
Other
17968 | Support next gen sequencing data | Short term solution is to support MAGE-TAB v1.1 columns & import, but not parse fastq, SAM, BAM.
28931 | Allow parseable data files to be IMPORTED NOT PARSED if parseable array design is not available. | Sometimes, normally parseable files (e.g., Agilent TXT) are rendered unparseable because the associated array design is ether absent or in an unparseable format. Currently, the system would fail the import of such data files. But the correct behaviour is for the system to import these data files without parsing. The user has the ability to later re-import these files if/when the appropriate parseable array design file becomes available. An example of this scenario is the set of TCGA Agilent experiments, which have array designs in the MAGE-TAB ADF (unparseable) format rather than in the Agilent GEML/xml (parseable) format. It should be possible to import such data files and keep them in the IMPORTED NOT PARSED state.
27012 | Genepix GPR data file validation must allow flexible column ordering.
Users/Collaborators
14630 | A collaborator who uploads files cannot see their own files in the manage data tab
26310 | Design a new UI for assigning permissions to samples | Review UI and see if we should implement in 2.5.0
Curation/Quality
13164 | Limit organisms to NCBI taxonomy term source only and clean up duplicates
14023 | Limit Material Type and Protocol Type terms to the MGED Ontologies
29040 | Suggest alternative terms and warn user about problematic annotations during MAGE-TAB import.
29041 | Let curators merge duplicate terms.
Performance
29072 | Prototype full text indexing like Lucene with view to improve search performance.
29071 | Cache experiment counts so that front page loads faster.
Search/Browse
29073 | Prototype enhanced browse functionality using faceted search techniques
22635 | Support searches for Experiment by Publication (by pubmed id and PI)
25128 | Search for and download Samples within an Experiment
20727 | Usability Enhancement: Add a button to "Show All" on all tabs under Annotation (could lead to slow page loads)
Misc
26303 | Upgrade to JBoss 5.1, except for upgrading from a previous installation
26304 | Implement support for JBoss 5.1 in the upgrade installers
26305 | Upgrade to Java 6
16610 | Support API access by Java 1.6 clients
29074 | Update documentation to reflect MySQL version 5.1
18758 | Support caArray Grid Service in JBOSS 4.0.5
10479 | Coverage > 80/70
21127 | Fix resetting of database state for integration tests
22546 | The add new Source/Sample/Extract/Labeled Extract/Hybridization GUI is broken in IE 8.
19044 | Need to add single-command-build and single command-deployment support to caArray build for BDA certification compliance. |  | Bill will talk to Anand about BDA compliance; partially resolved
18732 | Implement section 508 compliance (Reduction of issues by 30%) |  | Need to get 508 report run
28935 | Fix implementations of equals() and hashCode() for entities

## UploadDownload
artifact_id | summary | priority | COMPONENT | status | target_version | item_type | description_of_fix | COMMENTS
12119 | Allow files greater than 1 GB to be uploaded | 5 | Upload/Download | Submitted | 2.5.0 | Feature Enhancement
29034 | Upload/download manager: resumable downloads, transparent compression | 5 | Upload/Download | To Be Assessed | 2.5.0 | New Feature
29035 | Allow multiple file selection during upload | 4 | Upload/Download | To Be Assessed | Backlog | New Feature
13699 | Large upload job doesn't indicate completion, and Manage Data page makes it hard to infer completion. | 4 | Upload/Download | To Be Assessed | Backlog | Defect
28970 | SocketException: Broken pipe occurring during file upload | 3 | Upload/Download | Submitted | Backlog | Defect | A &quot;java.net.SocketException: Broken pipe&quot; is occurring frequently. It happens consistently on larger file uploads (both data files and array designs), such as when uploading the file L:\QA\MatthewRT\iterations\02\20298\20298_1.zip. It also happens more intermittently during during smaller file uploads. I have collected several of the errors, and compiled them into the attached file. In the log, file name preceding the error indicates the file being uploaded at the time of the error. The error is occurring after the file uploads are complete. The data file upload window ends up hanging at the &quot;Done&quot; state, and never transfers over to the page indicating a successful upload with the buttons to close the window and reload the Manage Data tab. The array design upload window displays a &quot;Bad Gateway&quot; page. However, the data files are in fact complete and fully accessible in caArray.
28976 | Some valid zip files cannot be uploaded. | 3 | Upload/Download | Submitted | Backlog | Defect | Maureen tried uploading the following zip file into caArray and it failed after 15 files: L:\NCICB\caArray\LCGWAS\bueto-00300\PeripheralBlood_SNP6.0Genotyping\AllCelFilesToRunSplitScript\17.files.zip The stack trace in the server log is attached, and it shows the following error: &quot;java.util.zip.ZipException: invalid entry size (expected 69043947 but got 69043880 bytes)&quot; I extracted the files from the zip and zipped it myself (by running &quot;zip&quot; on the command line on my Mac OS X 10.5.8). Uploading this zip to caArray was successful: L:\NCICB\caArray\LCGWAS\bueto-00300\PeripheralBlood_SNP6.0Genotyping\AllCelFilesToRunSplitScript\17.files.rezip.zip
25127 | Improve ability to download subsets of data | 3 | Upload/Download | Submitted | Backlog | Feature Enhancement | Related but different: GF 25128 (please read)
18733 | Adding button to upload popup page redirecting user back to uploads if datafiles uploaded are larger than 2GB | 1 | Upload/Download | Submitted | Backlog | Feature Enhancement

## Import
artifact_id | summary | priority | COMPONENT | status | target_version | item_type | description_of_fix
17430 | Split up import jobs into multiple transactions | 5 | Import | To Be Assessed | Backlog | New Feature
13114 | Add ability to see position of imports in Queue and perhaps managing the queue | 5 | Import | Submitted | 2.5.0 | New Feature
17968 | Allow upload and import of next gen sequencing data | 5 | Import | Submitted | 2.5.0 | New Feature
29047 | Investigate storing files on the file system instead of the database. | 5 | Import | To Be Assessed | Backlog | Feature Enhancement
28931 | Allow parseable data files to be IMPORTED NOT PARSED if parseable array design is not available. | 4 | Import | To Be Assessed | 2.5.0 | New Feature | Sometimes, normally parseable files (e.g., Agilent TXT) are rendered unparseable because the associated array design is ether absent or in an unparseable format. Currently, the system would fail the import of such data files. But the correct behaviour is for the system to import these data files without parsing. The user has the ability to later re-import these files if/when the appropriate parseable array design file becomes available. An example of this scenario is the set of TCGA Agilent experiments, which have array designs in the MAGE-TAB ADF (unparseable) format rather than in the Agilent GEML/xml (parseable) format. It should be possible to import such data files and keep them in the IMPORTED NOT PARSED state.
29036 | Investigate Postgres to get around database size/performance limits | 4 | Import | To Be Assessed | Backlog | Feature Enhancement
24791 | Add support for Term Accession Number column in MAGE-TAB | 4 | Import | Submitted | Backlog | Feature Enhancement | This allows specification of an accession number for a controlled vocabulary term in a mage-tab IDF or SDRF, as described in http://tab2mage.sourceforge.net/docs/sdrf.html#term_accession_number. This would be used to populate the accession field of the corresponding Term and could also be used to help locate an existing Term in our database. Questions to be resolved: - what to do if the name but not accession number match an existing term (or vice versa)
14371 | Provide UI-based mechanism for resolving import failure | 4 | Import | Clarification Required | Backlog | Defect
16913 | Image files not handled correctly during import/validate. | 4 | Import | Submitted | Backlog | Defect
27012 | Genepix GPR data file validation must allow flexible column ordering. | 4 | Import | To Be Assessed | 2.5.0 | Defect | PROBLEM: caArray expects the header in a Genepix GPR data file to be in the order {block, column, row}. On the other hand, the order does not matter in the GAL array design file. Jia and the curation team have pointed out that that GPR files sometimes have the following column ordering: {block, row, column}. This needs to be supported by making the column ordering flexible in our GPR validation code.
27703 | Support complex characteristics like sets and ranges in MAGE-TAB import | 4 | Import | To Be Assessed | Backlog | New Feature | The curators have run into this problem a few times. They want to enter sets of characteristics (e.g., disease states for a particular sample = &quot;AML&quot; from &quot;MGED Ontology&quot;, and also &quot;Down's Syndrome&quot; from &quot;NCI Thesaurus&quot;. An example for ranges is a Measurement Characteristic that represents &quot;30-40&quot; years old. In addition, Martin Morgan has requested this feature as well (being able to represent sets, ranges and lists).
10277 | ADDRESS incorrectly parsed; duplicate addresses | 3 | Import | Deferred | Backlog | Defect
14676 | Affymetrix CDF Handler does not connect logical probes, physical probes, and features | 3 | Import | Analyzed | Backlog | Defect
17037 | User can create duplicate experimental factors | 3 | Import | Analyzed | Backlog | Defect
19102 | Invalid measurement characteristic value should be flagged instead of throwing a stack trace | 3 | Import | Submitted | Backlog | Defect
21565 | Block Header Error in GAL File Due to Integer Requirement | 3 | Import | None | Backlog | Defect | We currently treat xOrigin and yOrigin as integers. However, it is possible for these numbers to be floats - they are distances measured in micrometers. We should change our code to allow floats.
23377 | MAGE-TAB Import/Update Fails Validation for Non-Sys Admin | 3 | Import | None | Backlog | Defect
24114 | Missing Labeled Extract Name column in SDRF generates java error messages | 3 | Import | Submitted | Backlog | Defect
26392 | New protocols are not created if a pre-existing protocol of the same name but different type exists | 3 | Import | Clarification Required | Backlog | Defect | This bug involves the auto creation of protocols from IDFs. Imagine a protocol in an IDF that has the same name as an already-existing protocol, but is of a different type. When the IDF is imported, a new protocol will not be created, even though the type is different. The already-existing protocol with the same name will get assigned to the newly-imported data. (The new protocol type will get created.) The clearest way to see this bug is to reproduce it on a fresh installation of caArray, though it does also happen on the tiers (I saw this on QA-VM). First, import the data archive L:QAMatthewRTiterationsÇ97Ç97.zip into an experiment for the Test3 design. The data will successfully export as GEO SOFT. Create another experiment (Test3 again) and import the archive L:QAMatthewRTiterations est est.zip. The IDF in the test archive contains all protocols of the same name as before, but their types are all appended with &amp;quot;_test&amp;quot;. After importing the data, it will still export as GEO SOFT. Navigating to Manage Protocols shows that no new protocols were created for the second data import.
28357 | Quantitation Types should be unique by name and design | 3 | Import | None | Backlog | Defect | Quantitation Types with the same name may be of different types depending on the design that defines them. see ArrayDaoImpl.getQuantitationType() called from DataSetImporter.getQuantitationTypes()
28695 | Any .csv file uploaded to an experiment is automatically typed as Illumina Design CSV | 3 | Import | Submitted | Backlog | Defect | For any .CSV file uploaded to an experiment, its type is automatically determined to be Illumina Design CSV. Since the file is being uploaded to an experiment, it should be typed as Illumina Data CSV, if anything. However, there are multiple types of supported CSV files (Agilent, ScanArray, and Illumina)so perhaps the default type for uploaded CSV files should be &quot;unknown&quot;.
28707 | Multiple associated array designs not recognized on Agilent miRNA data validation | 3 | Import | Submitted | Backlog | Defect | Create an experiment with associated miRNA array designs &quot;019118_D_20080214&quot; and &quot;Mouse miRNA Microarray 2.0&quot; (they're on QA). Upload the file L:\QA\MatthewRT\iterations\13\27280\27280.zip, and change the file type of the TXT files to Agilent Raw TXT. All of the files beginning with &quot;02&quot; use the &quot;Mouse miRNA Microarray 2.0&quot; design. Upon validation the file 02_valid.txt will fail validation, stating that there is &quot;No array design associated with this experiment&quot;. Note that validating 02_valid.txt in an experiment associated to only the Mouse array design does not cause an error.
15651 | Import functionality missing error message for files that fail validation | 3 | Import | Clarification Required | Backlog | Defect
16322 | cel file fail validation | 3 | Import | None | Backlog | Defect
16448 | Manage Data page: Filtering drop downs contain invalid list items | 3 | Import | Submitted | Backlog | Defect
17453 | Allow deletion of hybridizations without deleting the uploaded files themselves. | 3 | Import | To Be Assessed | Backlog | Feature Enhancement
18786 | increase the length of the Authors column in the &quot;Publication&quot; database table | 3 | Import | None | Backlog | Feature Enhancement
18967 | Enhance MAGE-TAB update feature to add/modify factor values for existing hybridizations. | 3 | Import | To Be Assessed | Backlog | Feature Enhancement
20515 | Allow the user to move supplemental files back to the Manage Data page with status = Uploaded. | 3 | Import | To Be Assessed | Backlog | Feature Enhancement
21852 | Improve Manage Data functionality by excluding array design types. | 3 | Import | To Be Assessed | Backlog | Feature Enhancement | 1. Inferring file types by looking inside the file will be covered by a different Gforge issue. This will solve the problem of an Illumina CSV file being inferred correctly. 2. The &quot;Change File Type&quot; dropdown should be limited to data file types (no array design types). 3. An attempt to import array design files (like CDF) will still give the error it currently gives. No change required there.
24208 | Have more extensive warnings organized by category for MAGE-TAB | 3 | Import | To Be Assessed | Backlog | Feature Enhancement
24209 | Create MAGE-Tab templates for common scenarios | 3 | Import | To Be Assessed | Backlog | Feature Enhancement
27719 | need to add import warning functionality. | 3 | Import | None | Backlog | Feature Enhancement | need to add import warning functionality. currently, warnings are only displayed during validation, not import. The only way to get messages directly to the user during importing is by throwing an exception, which will cause the import to fail. this issue arose during work for issue: [#27006] Test3 data files failing to import.
15319 | support for multiple extract column | 3 | Import | Submitted | Backlog | New Feature
19349 | For two-colour experiments, make Label column in SDRF mandatory. | 3 | Import | To Be Assessed | Backlog | New Feature
22843 | Add a parser for GEO GPL format | 3 | Import | Submitted | Backlog | New Feature
27490 | Parse Affymetrix bpmap tiling array design | 3 | Import | To Be Assessed | Backlog | New Feature | The Affymetrix promoter tiling arrays don't come with a pgf, clf or cdf file, but only bpmap files. In order to create a new array design for these arrays the Garvan Institute uses aroma.affymetrix to convert the bpmap into a cdf which they then import into caArray. They would like caArray to validate/parse the Affymetrix bpmap array design format.
24237 | Experiment hung on file size over 1gb during validation | 3 | Import | None | Backlog | None
28351 | Validation mechanism to make sure 1 raw data file can only link to 1 hybridization | 3 | Import | None | Backlog | None
28366 | Automatic file type detection | 3 | Import | None | Backlog | None | Use a combination of -file magic number -file name -user selection to detect what files are being uploaded, and what parsers should be used. File names alone are not reliable. We should also promote the use of magic numbers in all files. Even in text files that have no headers, it would be nice to have the first line be a comment line line with a machine readable content description.
17743 | Empty Characteristic is imported as a blank Characteristic | 3 | Import | None | Backlog | None
15238 | NCI-60 aCGH data | 2 | Import | To Be Assessed | Backlog | Defect
11468 | MAGE-TAB Validation: Inconsistent Data and Design Not Caught in SDRF | 2 | Import | Analyzed | Backlog | Defect
13547 | MAGE-TAB IDF file with a protocol name with no asscoicated protocol type causes misallocation of protocol name | 2 | Import | Submitted | Backlog | Defect
13549 | grow protocols with MAGE-TAB experiments are ignored in GUI after import | 2 | Import | Submitted | Backlog | Defect
29308 | Root cause analysis of the hybridization deletion issue (GF29170) | 2 | Import | Submitted | Backlog | Task
13598 | IDF with missing Experiment Design imports, yet its marked as a required field in the GUI | 2 | Import | Submitted | Backlog | Defect
14927 | Import data files: Poor communication of not importing dataset when message of importing was given by UI | 2 | Import | Analyzed | Backlog | Defect
16987 | Ability to reset status of files stuck in Importing/Validating state. | 2 | Import | Submitted | Backlog | Feature Enhancement
14994 | support US data format. | 2 | Import | Submitted | Backlog | Feature Enhancement
8328 | Add Comment handling to MAGE-TAB parsing | 2 | Import | Submitted | Backlog | Feature Enhancement
8329 | Add Date, Performer, Description handing to SDRF parser | 2 | Import | Submitted | Backlog | Feature Enhancement
13550 | Protocol application image and array data not populated from MAGE-TAB | 2 | Import | Submitted | Backlog | Feature Enhancement
16326 | Handle PGF/CLF files with overlapping chip types | 2 | Import | None | Backlog | Feature Enhancement
16677 | case insensitive validation | 2 | Import | None | Backlog | Feature Enhancement
23872 | Provide ability to bulk-change biomaterial and hybridization names. | 2 | Import | To Be Assessed | Backlog | New Feature

## UsersCollaborators
artifact_id | summary | priority | COMPONENT | status | target_version | item_type | description_of_fix
14630 | A collaborator who uploads files cannot see their own files in the manage data tab | 4 | Users/Collaborators | To Be Assessed | 2.5.0 | Defect
15521 | Collaboration group ownership should not be tied to experiment ownership. | 4 | Users/Collaborators | Submitted | Backlog | New Feature
26310 | Design a new UI for assigning permissions to samples | 4 | Users/Collaborators | Deferred | 2.5.0 | Feature Enhancement | For read-selective or read-write-selective permissions, the current UI for assigning permissions to samples is really confusing. Design a new UI for doing this that makes it easy, fast, and clear to work with hundreds of samples. This issue is only to design the UI, not to implement it.
21409 | Permissions Audit Log does not track experiment ownership changes | 3 | Users/Collaborators | Submitted | Backlog | Defect
16973 | Limit username and pw field to a reasonable max size | 3 | Users/Collaborators | Submitted | Backlog | Code Improvement
21660 | The support email address and phone numbers should not be hardcoded to NCICB-appropriate values on account request confirmation page. | 3 | Users/Collaborators | None | Backlog | Defect
22650 | Network login password is not case sensitive | 3 | Users/Collaborators | Submitted | Backlog | Defect
16352 | can not assign or created collaboration group | 3 | Users/Collaborators | None | Backlog | Defect
18520 | Registration email sent by caArray contains ambiguously specified State. | 3 | Users/Collaborators | Analyzed | Backlog | Defect
28610 | Remove plus signs in Subject line of Auto-generated Email | 3 | Users/Collaborators | Submitted | Backlog | Defect | When you are browsing the list of Experiments, an email link may be included under the column Primary Contact. If you click on the email link, the browser will open up your default email application and start to compose a new email to the email address associated with that Experiment. This process also auto-generates a subject line based on the name of the Experiment. Using Outlook as the default Email application, when the subject line is generated, the plus sign is used in place of a space. I understand that the plus signs are probably necessary for forming the mailto link (because you can't use spaces there). If possible, it would be nice if we can replace the plus signs with spaces (or even underscores) once it shows up on the subject line. See attached screenshot for example of defect.
20321 | Active Directory LDAP is not currently supported by caArray. | 3 | Users/Collaborators | None | Backlog | Feature Enhancement
28456 | Enhance Change Ownership Feature To Search By Experiment | 3 | Users/Collaborators | None | Backlog | Feature Enhancement
19035 | Email notification of state change or permissions change | 3 | Users/Collaborators | To Be Assessed | Backlog | New Feature
19220 | Allow deletion of all data created by a particular user. | 3 | Users/Collaborators | To Be Assessed | Backlog | New Feature
19533 | Add new level of experiment permissions which allows collaborator to change permissions. | 3 | Users/Collaborators | To Be Assessed | Backlog | New Feature
28356 | Unexpected error encountered with expiring login | 3 | Users/Collaborators | None | Backlog | None
15837 | Clear button option on Collabration Groups page display 's members list. | 3 | Users/Collaborators | Submitted | Backlog | None
18546 | If one of the required fields on registration page fails validation the requested roles checkboxes all go unchecked again. | 3 | Users/Collaborators | None | Backlog | None
10378 | Fine grained access control | 2 | Users/Collaborators | Submitted | Backlog | Code Improvement
16124 | Enhance Manage Collaborators Usability | 2 | Users/Collaborators | Analyzed | Backlog | Feature Enhancement
16125 | Experiment permission screen makes it difficult to see what user has access to what, as well as who has access to what sample | 2 | Users/Collaborators | Analyzed | Backlog | Feature Enhancement
20557 | Manage Ownership ,User name coloumn is not Alphabetically order | 2 | Users/Collaborators | To Be Assessed | Backlog | None

## CurationQuality
artifact_id | summary | priority | COMPONENT | status | target_version | item_type | description_of_fix
13164 | Limit organisms to NCBI taxonomy term source only | 5 | Curation/Quality | To Be Assessed | 2.5.0 | Feature Enhancement
29399 | Write an upgrade script that will clean up duplicate organisms in the database to limit them to the NCBI taxonomy term source. | 5 | Curation/Quality | To Be Assessed | 2.5.0 | Feature Enhancement
14023 | Limit Material Type and Protocol Type terms to the MGED Ontologies | 5 | Curation/Quality | Submitted | 2.5.0 | Feature Enhancement
29400 | Write an upgrade script that will clean up duplicate material types and protocol types in the database to limit them to the MGED ontology term source. | 5 | Curation/Quality | To Be Assessed | 2.5.0 | Feature Enhancement
29040 | Suggest alternative terms and warn user about problematic annotations during MAGE-TAB import. | 5 | Curation/Quality | To Be Assessed | Backlog | New Feature
29041 | Let curators merge duplicate terms. | 5 | Curation/Quality | To Be Assessed | Backlog | New Feature
22570 | UI for general controlled vocabulary management | 4 | Curation/Quality | Submitted | Backlog | Feature Enhancement
14833 | A single Human_WG-6 imported array design is both Affymetrix and Illumina at the same time | 4 | Curation/Quality | To Be Assessed | Backlog | Defect
24267 | Existing experiments need their Scan and Normalization protocol applications scrubbed | 4 | Curation/Quality | Submitted | Backlog | Defect | One suggestion is to enhance MAGE-TAB update to be able to update protocol information, and then provide documentation to tell users how to import a new MAGE-TAB that fixes this problem.
17978 | Restrict vocabulary and protocol editing to Curator role. | 3 | Curation/Quality | To Be Assessed | Backlog | Feature Enhancement
24584 | Protocol type filter contains ambiguous entries | 3 | Curation/Quality | Submitted | Backlog | Code Improvement | We should include the source in the Protocol Type drop-down, just as we do when adding a new Protocol, to reduce confusion.
15040 | Use array design manufacturer to set LSID and perform validation | 3 | Curation/Quality | None | Backlog | Code Improvement
29042 | Indicate MIAME compliance | 3 | Curation/Quality | None | Backlog | New Feature
29042 | Indicate MINSEQE compliance | 3 | Curation/Quality | None | Backlog | New Feature
10166 | Duplicate persons exist | 3 | Curation/Quality | Deferred | Backlog | Defect | see notes
13237 | Expand/re-evaluate the Assay Type list | 3 | Curation/Quality | Analyzed | Backlog | Defect
13949 | reuse existing genes by symbol name in GENE table | 3 | Curation/Quality | Submitted | Backlog | Feature Enhancement
22571 | Support flexible validation profiles for experiments | 3 | Curation/Quality | Submitted | Backlog | New Feature
15858 | A public caArray 1.6 Experiment becomes private, and nondownloadable, after migration to caArray 2.0 | 2 | Curation/Quality | Submitted | Backlog | Defect
13001 | Legacy data may contain incorrect Array information | 2 | Curation/Quality | Analyzed | Backlog | Defect

## caBIGIntegration
artifact_id | summary | priority | COMPONENT | status | target_version | item_type | description_of_fix
15168 | Grid security: Implement grid authentication in remote java API | 5 | Integration | Analyzed | 2.5.0 | New Feature
19782 | Grid security: Set up build/installer infrastructure needed for secure grid services | 5 | Integration | Analyzed | 2.5.0 | New Feature
19783 | Grid security: Integrate CGMM | 5 | Integration | Analyzed | 2.5.0 | New Feature
29076 | Do requirements specification for integration with biospecimen systems like caTissue | 5 | Integration | To Be Assessed | 2.5.0 | New Feature
29043 | Integrate with NES/COPPA | 4 | Integration | To Be Assessed | Backlog | New Feature
17118 | Complete MAGE-TAB export feature by adding remaining fields | 5 | Integration | Submitted | Backlog | Feature Enhancement
29044 | Writable APIs to create expt, upload and import data | 5 | Integration | To Be Assessed | 2.5.0 | New Feature
29045 | Look up annotations for biomaterials from a biospecimen system like caTissue | 5 | Integration | To Be Assessed | Backlog | New Feature
29046 | Investigate the use of CDEs to map Characteristic categories and Factors | 5 | Integration | To Be Assessed | Backlog | New Feature
28258 | Implement plugin architecture for platform parsers | 4 | Integration | Analyzed | 2.5.0 | Feature Enhancement | Building on 26557, we will implement the third piece of the components enumerated there: - a full plugin architecture with a registration system for data types and parsers
20302 | Grid security: Implement bulk-migration of CSM to Grid accounts if those accounts are on a known LDAP server that will be grid enabled | 4 | Integration | To Be Assessed | 2.5.0 | New Feature
14772 | Provide the ability to reuse biomaterials across experiments. | 3 | Integration | Submitted | Backlog | New Feature
14818 | Support the capture of external Experiment ID | 3 | Integration | Submitted | Backlog | New Feature
10340 | Entering &amp;amp;quot;PubMed ID&amp;amp;quot; value pulls data from NCBI pubmed server | 2 | Integration | Submitted | Backlog | New Feature
22626 | Characteristics for copied biomaterial are not exported in MAGE-TAB | 3 | Integration | To Be Assessed | Backlog | Defect
13101 | Add pretty URLs (of the http://array.nci.nih.gov/caarray/project/admin-00001) for other concepts in the system | 3 | Integration | To Be Assessed | Backlog | New Feature
28361 | Hybridization name that end with .E(for example:5500024056197041909864.E10 ) autamatically changed to scientific notation when exporting the sdrf file | 3 | Integration | None | Backlog | None

## Performance
artifact_id | summary | priority | COMPONENT | status | target_version | item_type | description_of_fix
29072 | Prototype full text indexing like Lucene with view to improve search performance. | 5 | Performance | To Be Assessed | 2.5.0 | Feature Enhancement
23325 | Improve the performance of biomaterial and other searches using Lucene-style indexing. | 5 | Performance | Submitted | Backlog | Defect
29071 | Cache experiment counts so that front page loads faster. | 4 | Performance | To Be Assessed | 2.5.0 | Feature Enhancement
29048 | Cache public data to improve performance. | 4 | Performance | To Be Assessed | Backlog | Feature Enhancement
22460 | Download link for biomaterials on search result lists (and probably other pages as well) is generated inefficiently | 4 | Performance | Submitted | Backlog | Feature Enhancement
20911 | Implement recommendations from Steve Souders' Web Optimization Techniques | 3 | Performance | Submitted | Backlog | Code Improvement
26326 | Implement performance improvements for struts | 3 | Performance | Submitted | Backlog | Code Improvement | Now that we have CSM performance enhancements, there are other areas where we can address application performance and make a difference (before, these were dominated by the CSM issueS). One such is in how we use Struts2. recommendations for performance tuning are here: http://cwiki.apache.org/WW/performance-tuning.html. particularly freemarker templates caching could be useful (or using the new Java-based templates from struts 2.1). See this diff from glassbox for some changes they made: svn diff -r1135:1142 https://svn.5amsolutions.com/corp/software/glassbox/trunk
28386 | DesignElementList gets too big, and should be able to be flushed in batchs. | 3 | Performance | None | Backlog | Code Improvement | When importing array data, the DesignElementList is fully built in memory, and Probes that are loaded remain in the session until the end of the import. We should build this list and save in smaller chunks, and evict Probes and other object from the session at the end of the batch.
18372 | Array design import is slow on STAGE | 3 | Performance | To Be Assessed | Backlog | Defect
17566 | Javascript does not perform well on pages that display a large number of files. | 3 | Performance | To Be Assessed | Backlog | Defect
16629 | PGF Array Design Import is too Slow | 3 | Performance | To Be Assessed | Backlog | Feature Enhancement
28367 | punt ProbeLookup | 3 | Performance | None | Backlog | None | All it does is map probes my name. It also invites data handler writers to load all design probes in memory at once, which is generally a problem for large designs.
14506 | look into adding a gzip filter of html content | 2 | Performance | None | Backlog | Defect

## SearchBrowse
artifact_id | summary | priority | COMPONENT | status | target_version | item_type | description_of_fix
29073 | Prototype enhanced browse functionality using faceted search techniques | 5 | Search/Browse | To Be Assessed | 2.5.0 | Feature Enhancement
16225 | Enhance browse functionality | 5 | Search/Browse | To Be Assessed | Backlog | Feature Enhancement
25128 | Search for and download Samples within an Experiment | 4 | Search/Browse | None | 2.5.0 | Feature Enhancement
22635 | Support searches for Experiment by Publication | 4 | Search/Browse | Submitted | 2.5.0 | New Feature
20727 | Usability Enhancement: Add a button to &lt;Show All&gt; on all tabs under Annotation | 4 | Search/Browse | Submitted | 2.5.0 | Feature Enhancement
22462 | Sample search should be changed into biomaterial search and brought into alignment with biomaterial keyword search from the API | 4 | Search/Browse | Submitted | Backlog | Feature Enhancement
26954 | Deleting multiple experiments simultaneously results in an error | 3 | Search/Browse | Submitted | Backlog | Code Improvement | This error occurs when attempting to delete multiple experiments in quick succession, without waiting for confirmation that an experiment has been deleted before proceeding to the next deletion action. The message &amp;amp;quot;An unexpected Error has occurred&amp;amp;quot; with the Java error message is displayed. I have seen three different errors occur, all of which are captured in the attached files.
18096 | Experiment Design Types and Experiment Design Description are inaccurately labelled as required fields. | 3 | Search/Browse | Submitted | Backlog | Defect
22640 | Experiment Title in My Experiment Workspace does not sort properly | 3 | Search/Browse | To Be Assessed | Backlog | Defect | Data clean up - removed leading empty space, just on title.
22683 | Hybridization count not correct | 3 | Search/Browse | Submitted | Backlog | Defect
27213 | Formatting differences b/w IE and Firefox in the Experiment Details view | 3 | Search/Browse | Submitted | Backlog | Defect | Array Designs list does not expand in IE when many array designs are displayed (when creating an experiment or editing its Overview) The accordian pages in the Download Data subtab have some formatting issues: 1. All accordian pages: A. No padding between edge of accordian panes and objects (everything is crammed up to the left-top of the frames) 2. Top accordian page (Download Experiment File Packages): A. Gray lines are presesnt between the different download options in Firefox, but not in IE B. In Firefox, the text is displayed directly to the left of the text; in IE the text is below the icon 3. Second accordian page (Download Selected Experiment Files): A. Buttons are attached to the bottom of the table in IE; in Firefox they are attached to the bottom of the accordian pane 4. Third accordian page (Export Experiment Annotation Packages): A. Most of the formatting is gone in IE, while in Firefox the page is laid out better. There are too many differences to list out, so the attached screenshot shows the differences between the two browsers.
27462 | Delete button in Manage Data subtab is activated with clicks outside of the button itself | 3 | Search/Browse | Submitted | Backlog | Defect | This only occurs in IE 8 (also tested in IE 7, FF 3.6, FF 3.0). Go to the Manage Data subtab in any experiment. The buttons at the bottom of the table (Delete, Unpack Archive, etc.) all sit in a small gray pane. Clicking (or hovering) on this pane anywhere outside of one of the buttons activates (or highlights) the Delete button, as if the Delete button covers the entire pane.
28445 | Need space in page navigation link on Experiments list | 3 | Search/Browse | Submitted | Backlog | Defect | When viewing My Experiment Workspace or browsing Experiments, and when the list of experiments are in multiple pages, there is a space missing in the page navigation links on top of the list of experiments. See attached screenshots for example (the issue is encircled in red). A space is required after a page number link when the page number is at the end. A space is required before the page number link when the page is at the beginning.
15138 | Usability: Repeated searches are hard to do (no link to Search caArray portlet) | 3 | Search/Browse | Submitted | Backlog | Defect
16571 | display of source and sample detail | 3 | Search/Browse | None | Backlog | Feature Enhancement
18388 | Handling of investigators and main point of contact should be clarified. | 3 | Search/Browse | To Be Assessed | Backlog | Feature Enhancement
22608 | Add capability to enter html links into Overview -&gt; Experiment Description field | 3 | Search/Browse | None | Backlog | Feature Enhancement
20541 | History and versioning of experiments | 3 | Search/Browse | To Be Assessed | Backlog | New Feature

## Misc
artifact_id | summary | priority | COMPONENT | status | target_version | item_type | description_of_fix | COMMENTS
26303 | Upgrade to JBoss 5.1, except for upgrading from a previous installation | 4 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | Upgrade application to work with JBoss 5.1. This issue includes making this work for local and remote tiers and clean installs, but not upgrade installs - that will be covered by a separate issue.
26304 | Implement support for JBoss 5.1 in the upgrade installers | 4 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | Implement support for upgrading to JBoss 5.1 in the upgrade installers (GUI and command line). This includes moving over the relevant configuration.
26305 | Upgrade to Java 6 | 4 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | Upgrade application to work with Java 6. The application will not need to work with Java 5 after this.
16610 | Support API access by Java 1.6 clients | 4 | API | Submitted | deferred | Feature Enhancement
29074 | Update documentation to reflect MySQL version 5.1 | 4 | Documentation | To Be Assessed | 2.5.0 | Documentation Update
18758 | Support caArray Grid Service in JBOSS 4.0.5 | 4 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Feature Enhancement
10479 | Coverage > 80/70 | 4 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
21127 | Fix resetting of database state for integration tests | 4 | Tech Stack/Tech Debt | To Be Assessed | 2.5.0 | Code Improvement
22546 | The add new Source/Sample/Extract/Labeled Extract/Hybridization GUI is broken in IE 8. | 4 | Tech Stack/Tech Debt | Submitted | None | Defect
19044 | Need to add single-command-build and single command-deployment support to caArray build for BDA certification compliance. | 4 | Tech Stack/Tech Debt | None | None | Defect |  | Bill will talk to Anand about BDA compliance; partially resolved
18732 | Implement section 508 compliance (Reduction of issues by 30%) | 4 | UI | To Be Assessed | deferred | Defect |  | Need to get 508 report run
28935 | Fix implementations of equals() and hashCode() for entities | 4 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | equals and hashCode are currently based on ID. this is not the recommended Hibernate approach, and causes problems: - if any classes define compareTo, it is generally based on some other field and thus incompatible with the above implementations - making an object persistent (taking id from null to non-null) changes the hashCode of an object, which is problematic. Instead, per hibernate recommendation, we should base equals/hashCode on the natural (business) key, ideally immutable.
29207 | Reduce CI build time to 15 minutes. | 3 | Tech Stack/Tech Debt | To Be Assessed | 2.5.0 | Code Improvement
29208 | Improve build time on CI machine to match local times. | 3 | Tech Stack/Tech Debt | To Be Assessed | 2.5.0 | Code Improvement
29170 | Unexpected error while deleting hybridization | 4 | Import | None | 2.5.0 | Defect
17785 | Installer must support configuring SSL support in JBoss | 3 | Installer | Submitted | 2.5.0 | Defect
19858 | 2.2.0 gui installer on download center page fails installation -https://gforge.nci.nih.gov/frs/?group_id=450 | 3 | Installer | To Be Assessed | None | Defect
13859 | No API provided to logout through the Remote Java API, causing anonymous user to gain access to previous credentialed user's private data. | 4 | API | Submitted | deferred | Defect
20822 | Legacy Grid API serialization does not match the XSDs for single-valued associations | 4 | API | Submitted | 2.5.0 | Defect | Fix by modifying the XSD to conform to the code.
22230 | getAllCharacteristicCategories returns fewer than expected results for &quot;QA Affymetrix Experiment for API Testing&quot;. | 4 | API | Submitted | None | Defect
22694 | Grid API enumerateBiomaterialByKeyword does not return expected results for null keyword. | 4 | API | Verification failed | deferred | Defect
22718 | Grid API - enumerateFiles does not return expected results. | 4 | API | Submitted | 2.5.0 | Defect
26127 | CQL or example search involving ArrayDesign fails when using Remote EJB Legacy API | 4 | API | Verification failed | 2.5.0 | Defect | This was found in test case 382 of the CQL tests in the QA API Legacy Test Suite. It can be reproduced with an CQL or example search that references ArrayDesign, either as the target or directly associated entity. The stack trace is: [java] java.io.InvalidClassException: gov.nih.nci.caarray.domain.array.ArrayDesign; local class incompatible: stream classdesc serialVersionUID = -7772722455117790401, local class serialVersionUID = 1234567890 [java] at java.io.ObjectStreamClass.initNonProxy(ObjectStreamClass.java:546) [java] at java.io.ObjectInputStream.readNonProxyDesc(ObjectInputStream.java:1552) [java] at java.io.ObjectInputStream.readClassDesc(ObjectInputStream.java:1466) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1699) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.readObject(ObjectInputStream.java:348) [java] at java.util.HashMap.readObject(HashMap.java:1066) [java] at sun.reflect.NativeMethodAccessorImpl.invoke0(Native Method) [java] at sun.reflect.NativeMethodAccessorImpl.invoke(NativeMethodAccessorImpl.java:39) [java] at sun.reflect.DelegatingMethodAccessorImpl.invoke(DelegatingMethodAccessorImpl.java:25) [java] at java.lang.reflect.Method.invoke(Method.java:592) [java] at java.io.ObjectStreamClass.invokeReadObject(ObjectStreamClass.java:946) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1812) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.defaultReadFields(ObjectInputStream.java:1910) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1834) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.defaultReadFields(ObjectInputStream.java:1910) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1834) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.readObject(ObjectInputStream.java:348) [java] at java.util.ArrayList.readObject(ArrayList.java:591) [java] at sun.reflect.NativeMethodAccessorImpl.invoke0(Native Method) [java] at sun.reflect.NativeMethodAccessorImpl.invoke(NativeMethodAccessorImpl.java:39) [java] at sun.reflect.DelegatingMethodAccessorImpl.invoke(DelegatingMethodAccessorImpl.java:25) [java] at java.lang.reflect.Method.invoke(Method.java:592) [java] at java.io.ObjectStreamClass.invokeReadObject(ObjectStreamClass.java:946) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1812) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.readObject(ObjectInputStream.java:348) [java] at org.jboss.aop.joinpoint.InvocationResponse.readExternal(InvocationResponse.java:122) [java] at java.io.ObjectInputStream.readExternalData(ObjectInputStream.java:1756) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1717) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.defaultReadFields(ObjectInputStream.java:1910) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1834) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.readObject(ObjectInputStream.java:348) [java] at org.jboss.remoting.serialization.impl.java.JavaSerializationManager.receiveObject(JavaSerializationManager.java:128) [java] at org.jboss.remoting.marshal.serializable.SerializableUnMarshaller.read(SerializableUnMarshaller.java:66) [java] at org.jboss.remoting.transport.socket.SocketClientInvoker.transport(SocketClientInvoker.java:280) [java] at org.jboss.remoting.RemoteClientInvoker.invoke(RemoteClientInvoker.java:143) [java] at org.jboss.remoting.Client.invoke(Client.java:525) [java] at org.jboss.remoting.Client.invoke(Client.java:488) [java] at org.jboss.aspects.remoting.InvokeRemoteInterceptor.invoke(InvokeRemoteInterceptor.java:55) [java] at org.jboss.aop.joinpoint.MethodInvocation.invokeNext(MethodInvocation.java:101) [java] at org.jboss.aspects.tx.ClientTxPropagationInterceptor.invoke(ClientTxPropagationInterceptor.java:61) [java] at org.jboss.aop.joinpoint.MethodInvocation.invokeNext(MethodInvocation.java:101) [java] at org.jboss.aspects.security.SecurityClientInterceptor.invoke(SecurityClientInterceptor.java:53) [java] at org.jboss.aop.joinpoint.MethodInvocation.invokeNext(MethodInvocation.java:101) [java] at org.jboss.ejb3.remoting.IsLocalInterceptor.invoke(IsLocalInterceptor.java:77) [java] at org.jboss.aop.joinpoint.MethodInvocation.invokeNext(MethodInvocation.java:101) [java] at org.jboss.ejb3.stateless.StatelessRemoteProxy.invoke(StatelessRemoteProxy.java:102) [java] at $Proxy0.search(Unknown Source) [java] at caarray.client.examples.search.java.ApiSearchExperimentByExample.searchExperiments(ApiSearchExperimentByExample.java:175) [java] at caarray.client.examples.search.java.ApiSearchExperimentByExample.main(ApiSearchExperimentByExample.java:129) [java] at sun.reflect.NativeMethodAccessorImpl.invoke0(Native Method) [java] at sun.reflect.NativeMethodAccessorImpl.invoke(NativeMethodAccessorImpl.java:39) [java] at sun.reflect.DelegatingMethodAccessorImpl.invoke(DelegatingMethodAccessorImpl.java:25) [java] at java.lang.reflect.Method.invoke(Method.java:592) [java] at org.apache.tools.ant.taskdefs.ExecuteJava.run(ExecuteJava.java:217) [java] at org.apache.tools.ant.taskdefs.ExecuteJava.execute(ExecuteJava.java:152) [java] at org.apache.tools.ant.taskdefs.Java.run(Java.java:764) [java] at org.apache.tools.ant.taskdefs.Java.executeJava(Java.java:218) [java] at org.apache.tools.ant.taskdefs.Java.executeJava(Java.java:132) [java] at org.apache.tools.ant.taskdefs.Java.execute(Java.java:105) [java] at org.apache.tools.ant.UnknownElement.execute(UnknownElement.java:288) [java] at sun.reflect.NativeMethodAccessorImpl.invoke0(Native Method) [java] at sun.reflect.NativeMethodAccessorImpl.invoke(NativeMethodAccessorImpl.java:39) [java] at sun.reflect.DelegatingMethodAccessorImpl.invoke(DelegatingMethodAccessorImpl.java:25) [java] at java.lang.reflect.Method.invoke(Method.java:592) [java] at org.apache.tools.ant.dispatch.DispatchUtils.execute(DispatchUtils.java:106) [java] at org.apache.tools.ant.Task.perform(Task.java:348) [java] at org.apache.tools.ant.Target.execute(Target.java:357) [java] at org.apache.tools.ant.Target.performTasks(Target.java:385) [java] at org.apache.tools.ant.Project.executeSortedTargets(Project.java:1337) [java] at org.apache.tools.ant.Project.executeTarget(Project.java:1306) [java] at org.apache.tools.ant.helper.DefaultExecutor.executeTargets(DefaultExecutor.java:41) [java] at org.apache.tools.ant.Project.executeTargets(Project.java:1189) [java] at org.apache.tools.ant.Main.runBuild(Main.java:758) [java] at org.apache.tools.ant.Main.startAnt(Main.java:217) [java] at org.apache.tools.ant.launch.Launcher.run(Launcher.java:257) [java] at org.apache.tools.ant.launch.Launcher.main(Launcher.java:104) [java] Generic error. [java] java.lang.reflect.UndeclaredThrowableException [java] at $Proxy0.search(Unknown Source) [java] at caarray.client.examples.search.java.ApiSearchExperimentByExample.searchExperiments(ApiSearchExperimentByExample.java:175) [java] at caarray.client.examples.search.java.ApiSearchExperimentByExample.main(ApiSearchExperimentByExample.java:129) [java] at sun.reflect.NativeMethodAccessorImpl.invoke0(Native Method) [java] at sun.reflect.NativeMethodAccessorImpl.invoke(NativeMethodAccessorImpl.java:39) [java] at sun.reflect.DelegatingMethodAccessorImpl.invoke(DelegatingMethodAccessorImpl.java:25) [java] at java.lang.reflect.Method.invoke(Method.java:592) [java] at org.apache.tools.ant.taskdefs.ExecuteJava.run(ExecuteJava.java:217) [java] at org.apache.tools.ant.taskdefs.ExecuteJava.execute(ExecuteJava.java:152) [java] at org.apache.tools.ant.taskdefs.Java.run(Java.java:764) [java] at org.apache.tools.ant.taskdefs.Java.executeJava(Java.java:218) [java] at org.apache.tools.ant.taskdefs.Java.executeJava(Java.java:132) [java] at org.apache.tools.ant.taskdefs.Java.execute(Java.java:105) [java] at org.apache.tools.ant.UnknownElement.execute(UnknownElement.java:288) [java] at sun.reflect.NativeMethodAccessorImpl.invoke0(Native Method) [java] at sun.reflect.NativeMethodAccessorImpl.invoke(NativeMethodAccessorImpl.java:39) [java] at sun.reflect.DelegatingMethodAccessorImpl.invoke(DelegatingMethodAccessorImpl.java:25) [java] at java.lang.reflect.Method.invoke(Method.java:592) [java] at org.apache.tools.ant.dispatch.DispatchUtils.execute(DispatchUtils.java:106) [java] at org.apache.tools.ant.Task.perform(Task.java:348) [java] at org.apache.tools.ant.Target.execute(Target.java:357) [java] at org.apache.tools.ant.Target.performTasks(Target.java:385) [java] at org.apache.tools.ant.Project.executeSortedTargets(Project.java:1337) [java] at org.apache.tools.ant.Project.executeTarget(Project.java:1306) [java] at org.apache.tools.ant.helper.DefaultExecutor.executeTargets(DefaultExecutor.java:41) [java] at org.apache.tools.ant.Project.executeTargets(Project.java:1189) [java] at org.apache.tools.ant.Main.runBuild(Main.java:758) [java] at org.apache.tools.ant.Main.startAnt(Main.java:217) [java] at org.apache.tools.ant.launch.Launcher.run(Launcher.java:257) [java] at org.apache.tools.ant.launch.Launcher.main(Launcher.java:104) [java] Caused by: java.rmi.MarshalException: Failed to communicate. Problem during marshalling/unmarshalling; nested exception is: [java] java.io.InvalidClassException: gov.nih.nci.caarray.domain.array.ArrayDesign; local class incompatible: stream classdesc serialVersionUID = -7772722455117790401, local class serialVersionUID = 1234567890 [java] at org.jboss.remoting.transport.socket.SocketClientInvoker.transport(SocketClientInvoker.java:307) [java] at org.jboss.remoting.RemoteClientInvoker.invoke(RemoteClientInvoker.java:143) [java] at org.jboss.remoting.Client.invoke(Client.java:525) [java] at org.jboss.remoting.Client.invoke(Client.java:488) [java] at org.jboss.aspects.remoting.InvokeRemoteInterceptor.invoke(InvokeRemoteInterceptor.java:55) [java] at org.jboss.aop.joinpoint.MethodInvocation.invokeNext(MethodInvocation.java:101) [java] at org.jboss.aspects.tx.ClientTxPropagationInterceptor.invoke(ClientTxPropagationInterceptor.java:61) [java] at org.jboss.aop.joinpoint.MethodInvocation.invokeNext(MethodInvocation.java:101) [java] at org.jboss.aspects.security.SecurityClientInterceptor.invoke(SecurityClientInterceptor.java:53) [java] at org.jboss.aop.joinpoint.MethodInvocation.invokeNext(MethodInvocation.java:101) [java] at org.jboss.ejb3.remoting.IsLocalInterceptor.invoke(IsLocalInterceptor.java:77) [java] at org.jboss.aop.joinpoint.MethodInvocation.invokeNext(MethodInvocation.java:101) [java] at org.jboss.ejb3.stateless.StatelessRemoteProxy.invoke(StatelessRemoteProxy.java:102) [java] ... 30 more [java] Caused by: java.io.InvalidClassException: gov.nih.nci.caarray.domain.array.ArrayDesign; local class incompatible: stream classdesc serialVersionUID = -7772722455117790401, local class serialVersionUID = 1234567890 [java] at java.io.ObjectStreamClass.initNonProxy(ObjectStreamClass.java:546) [java] at java.io.ObjectInputStream.readNonProxyDesc(ObjectInputStream.java:1552) [java] at java.io.ObjectInputStream.readClassDesc(ObjectInputStream.java:1466) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1699) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.readObject(ObjectInputStream.java:348) [java] at java.util.HashMap.readObject(HashMap.java:1066) [java] at sun.reflect.NativeMethodAccessorImpl.invoke0(Native Method) [java] at sun.reflect.NativeMethodAccessorImpl.invoke(NativeMethodAccessorImpl.java:39) [java] at sun.reflect.DelegatingMethodAccessorImpl.invoke(DelegatingMethodAccessorImpl.java:25) [java] at java.lang.reflect.Method.invoke(Method.java:592) [java] at java.io.ObjectStreamClass.invokeReadObject(ObjectStreamClass.java:946) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1812) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.defaultReadFields(ObjectInputStream.java:1910) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1834) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.defaultReadFields(ObjectInputStream.java:1910) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1834) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.readObject(ObjectInputStream.java:348) [java] at java.util.ArrayList.readObject(ArrayList.java:591) [java] at sun.reflect.NativeMethodAccessorImpl.invoke0(Native Method) [java] at sun.reflect.NativeMethodAccessorImpl.invoke(NativeMethodAccessorImpl.java:39) [java] at sun.reflect.DelegatingMethodAccessorImpl.invoke(DelegatingMethodAccessorImpl.java:25) [java] at java.lang.reflect.Method.invoke(Method.java:592) [java] at java.io.ObjectStreamClass.invokeReadObject(ObjectStreamClass.java:946) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1812) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.readObject(ObjectInputStream.java:348) [java] at org.jboss.aop.joinpoint.InvocationResponse.readExternal(InvocationResponse.java:122) [java] at java.io.ObjectInputStream.readExternalData(ObjectInputStream.java:1756) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1717) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.defaultReadFields(ObjectInputStream.java:1910) [java] at java.io.ObjectInputStream.readSerialData(ObjectInputStream.java:1834) [java] at java.io.ObjectInputStream.readOrdinaryObject(ObjectInputStream.java:1719) [java] at java.io.ObjectInputStream.readObject0(ObjectInputStream.java:1305) [java] at java.io.ObjectInputStream.readObject(ObjectInputStream.java:348) [java] at org.jboss.remoting.serialization.impl.java.JavaSerializationManager.receiveObject(JavaSerializationManager.java:128) [java] at org.jboss.remoting.marshal.serializable.SerializableUnMarshaller.read(SerializableUnMarshaller.java:66) [java] at org.jboss.remoting.transport.socket.SocketClientInvoker.transport(SocketClientInvoker.java:280) [java] ... 42 more
22908 | Allow API search of files by name within an experiment. | 4 | API | To Be Assessed | deferred | Feature Enhancement
19644 | Error during import of Genepix gal file | 4 | Array Designs | Submitted | deferred | Defect
20136 | Import of a typical Genepix GAL array design exceeds default transaction timeout. | 4 | Array Designs | Clarification Required | deferred | Defect |  | High priority
27128 | need to remove duplicate environment and env.name properties from installation and deployment properties files. | 4 | Installer | None | 2.5.0 | Code Improvement | need to remove duplicate environment and env.name properties from installation and deployment properties files. this was motivated by DRT https://system-requests-test.nci.nih.gov:7443/jira/browse/TASKMGT-3187
23936 | Local Installation Guide: no warning that caArray installation will fail if prior UPT installation uses its command line installer. | 4 | Installer | Submitted | None | Defect
20324 | caArray log4j misconfiguration issues. | 4 | Tech Stack/Tech Debt | None | None | Defect
22833 | Consider using RMI-over HTTP for EJB3 remote bean invocations to reduce number of ports that need to be open in the firewall | 3 | API | Coding Completed | 2.5.0 | Code Improvement
12031 | Object graph trimming/initialization leads to poor performance with large data sets | 3 | API | To Be Assessed | deferred | Defect
19804 | CQL processor does alphabetical comparison for numerical fields. | 3 | API | To Be Assessed | deferred | Defect
22855 | Grid API search for enumerateHybridizations do not return expected results | 3 | API | Submitted | 2.5.0 | Defect
22978 | Legacy API: searches for Samples with no restrictions result in an exception for both search-by-example and CQL searches. | 3 | API | Submitted | deferred | Defect
22982 | Legacy API: CaArrayFile searches with no restrictions do not return expected results. | 3 | API | Submitted | deferred | Defect
23927 | Legacy Grid API: Can't navigate from hybridization to labeledExtracts. | 3 | API | Submitted | None | Defect
16608 | CQL queries returning incorrect results via the Grid API | 3 | API | To Be Assessed | None | Defect
23487 | Consider making FileType into entity instead of type | 3 | API | Submitted | 2.5.0 | Feature Enhancement
23489 | Consider having a separate set of classes for use in example query | 3 | API | Submitted | 2.5.0 | Feature Enhancement
21627 | CQL query processor returns incorrect results for OR query when association is null. | 3 | API | To Be Assessed | 2.5.0 | None | fix by upgrade of new sdk processor.
28703 | castor won't populate properties with private setters/constructors | 3 | API | None | 2.5.0 | None | even though hibernate will allow private setter, castor won't. Domain beans will be marshalled properly, but one cannot use castor to unmarshall the XML back into domain beans. Fields with private setter will remain null, and the ones with private ctors will not be created. We need to make sure that beans we intend to use over the grid have public read/write properties and ctors (possibly depricated). Or see if castor will allow a class descriptor that can provide custom accessors for those fiealds.
28404 | GenomewideSNP_5 and _6 array design import failure | 3 | Array Designs | Submitted | 2.5.0 | Defect | The array design GenomewideSNP_5 fails to import locally. No additional error message is given. The log is attached. Gax had been having trouble importing GenomewideSNP_6 as well, so I've decided to include it in this GForge item. GenomewideSNP_5 can be found at L:\QA\MatthewRT\iterations\06\Test_files\Array_Design_Files The reason two log files are attached: I couldn't tell which error was associated with the failure, so I ended up including more of the log file. Dan's comment from duplicate issue #28245: Very long import time; consider missing features. For 2.4.0, add to the release notes: Instructions to increase timeout in DB (to something like 12 hours).
28436 | File upload progress script in manage array designs seems broken | 3 | Array Designs | Submitted | 2.5.0 | Defect | When I upload an array design file, the progress report stuff does not seem to work well. Two things seem broken: - the progress bar doesn't really update - after the initial phase (when the upload is complete and the file is being processed), processor usage spikes and I eventually will get a &quot;unresponsive script&quot; dialog from firefox. I have encoountered this with a Nimblegen NDF design that has validation problems (described in Matt's comment for the Nimblegen NDF issue).
28912 | &quot;Permission Denied&quot; to upload array design file after InvalidDataFileException error | 3 | Array Designs | Submitted | None | Defect | To recreate: 1. Attempt to upload an array design (say, Test3) 2. When selecting the File Format for the array design, intentionally set it incorrectly (say, Nimblegen NDF) 3. Click Save to upload the array design 4. An error will occur, and the user can then again select an Array Design file to upload 5. Select the same array design again 6. Set the File Format correctly (or leave it to Automatic) 7. The process will halt, and the window will display the following message: Permission Denied User user does not have privilege PERMISSIONS for entity of type gov.nih.nci.caarray.domain.array.ArrayDesign with id 156 The only notable thing in the logs is the InvalidDataFileException, which I believe came from the intentionally bad upload. The log is attached.
16445 | Magage Array Design: No status = &quot;deleting&quot; when performing and array design delete | 3 | Array Designs | Submitted | None | Defect
17497 | Error uploading duplicate array design | 3 | Array Designs | None | 2.5.0 | Defect
16430 | Delete array designs in background | 3 | Array Designs | Analyzed | deferred | Feature Enhancement
16621 | &quot;HT_HG-U133A&quot; as known as &quot;U133AAofAv2&quot; | 3 | Array Designs | None | deferred | Feature Enhancement
25168 | Allow array designs with a custom provider. | 3 | Array Designs | To Be Assessed | deferred | New Feature | Some studies use customized array designs which are very specific and not commonly found in other studies. It is can not fit into any provider currently supported and it is most likely won't be reused in other studies to justified for an individual provider, therefore it is appropriate to include such designs in &quot;custom provider&quot;. An example for such a provider can be found in gforge curation tracker at: http://gforge.nci.nih.gov/tracker/?func=detail&amp;atid=2197&amp;aid=22556&amp;group_id=305
25971 | deleting an array design leaves behind gene and probeannotation rows. | 3 | Array Designs | Submitted | 2.5.0 | None
17883 | Latest caArray Install Guide has properties editing instructions too late to prevent backslash errors | 3 | Documentation | Submitted | None | Defect
24740 | Typo in index of user's guide | 3 | Documentation | Submitted | None | Documentation Update
24389 | Double URL in wiki post installation tasks | 3 | Documentation | Submitted | None | Documentation Update | https://wiki.nci.nih.gov/display/caArray2/Post+Installation+Tasks+caArray+2.3.0+-+Using+UPT+to+Add+caArray+Users In step 11, the UPT login URL is written twice in a row in the box.
24206 | Validate LDAP connection properties in installer if enabled | 3 | Installer | To Be Assessed | 2.5.0 | Code Improvement
26787 | installer should start jboss servers at end of installation process, after all cfg changes have been applied. | 3 | Installer | None | 2.5.0 | Code Improvement | installer should start jboss servers at end of installation process, after all cfg changes have been applied.
23532 | Update the list of &amp;quot;must-have&amp;quot; ports for command-line installer | 3 | Installer | Submitted | None | Defect
28263 | Node name is hard coded in header | 3 | Installer | Submitted | 2.5.0 | Defect | The header area of the caArray UI has &quot;Node: NCICB&quot;. The &quot;NCICB&quot; appears to be hardcoded. It should be changeable (via installation properties) to whatever the local installer wishes it to be. The same value should appear in the Location dropdown.
16572 | caArray installer DB configuration only works if &quot;localhost&quot; is specified as database.server property value. | 3 | Installer | Analyzed | None | Defect
16969 | Installer -upgrade - grid.static.hostname should correspond to domain.name from previous version installed | 3 | Installer | Submitted | None | Defect
17547 | Local installation with ldap.authentication.disabled=true does not disable LDAP | 3 | Installer | To Be Assessed | None | Defect
17420 | The caArray installer should allow configurable JBoss administrator username (currently hard-coded to &quot;admin&quot;) as the password is configurable. | 3 | Installer | Analyzed | None | Feature Enhancement
20826 | LDAP connection info should be validated by caArray installer. | 3 | Installer | None | None | Feature Enhancement | Ask BDA team to implement.
22085 | Add Property to Allow Labeling of Server Installation | 3 | Installer | None | deferred | Feature Enhancement
22835 | Need new image for National Cancer Institute logo on GUI installer | 3 | Installer | Submitted | None | Feature Enhancement
25505 | Consider adding check that installation is no earlier than 2.2.0 | 3 | Installer | Submitted | 2.5.0 | Feature Enhancement | Since our 2.4.0 Liquibase installer will only support directly upgrading from 2.2.0 or later, we should perhaps add a check early on in the GUI and command line installers that the users have a 2.2.0 or later installation
26297 | Grid science POC-related properties should be exposed in GUI installer. | 3 | Installer | None | 2.5.0 | Feature Enhancement | The install.properties file exposes several grid science POC-related properties which cannot be configured in the GUI installer, but should be. The properties: grid.poc.science.affiliation grid.poc.science.name.last grid.poc.science.name.first grid.poc.science.phone grid.poc.science.email grid.poc.science.role
17999 | Installer should support deployment configuration recommended by caGrid Deployment Technical Guide | 3 | Installer | To Be Assessed | 2.5.0 | New Feature
19084 | The caArray GUI installer should flexibly use master release notes, not seperate Readme.txt. | 3 | Installer | None | None | None
26306 | Upgrade to caGrid 1.3 | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | Upgrade to use caGrid 1.3 | Wait for 1.4 or 2.0
10096 | Improve Unexpected Error Handling | 3 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
11926 | Use different database for executing unit and integration tests | 3 | Tech Stack/Tech Debt | Analyzed | 2.5.0 | Code Improvement
14918 | Add support to SearchDao for queryUniqueResult() and queryRequiredUniqueResult | 3 | Tech Stack/Tech Debt | Submitted | None | Code Improvement
17841 | Separate MAGE-TAB export code from import code | 3 | Tech Stack/Tech Debt | To Be Assessed | None | Code Improvement
20910 | Scripts and Styles are not actually minified | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement
21128 | Refactor DAO layer | 3 | Tech Stack/Tech Debt | To Be Assessed | 2.5.0 | Code Improvement
24117 | Refactor MAG-TAB and GEO SOFT export subsystem | 3 | Tech Stack/Tech Debt | None | None | Code Improvement
24440 | Improve MageTb parser my using an event driven parser. | 3 | Tech Stack/Tech Debt | None | None | Code Improvement | A more efficient MageTab parser could be created using an event driver metaphor like SAX, avoiding the intermediate model. Consider using existing MAGE-TAB parser like Limpopo (from EBI) instead. Other application ArrayExpress, Annotare etc. use it, and they are open to having a caArray-specific validator plugin.
26308 | Punt ajaxtags and displaytag libraries; find other implementations of data table and tabs | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | Punt usage of ajax_tags and displaytag. Replace our tabs implementation and data tables (the two main things we use the above for) by leveraging a different library. Possible implementations: tabs: scriptaculous: http://wiki.github.com/madrobby/scriptaculous/tabs yui: http://developer.yahoo.com/yui/tabview/ jquery UI: http://jqueryui.com/demos/tabs/ Ext JS: http://www.extjs.com/deploy/dev/examples/tabs/tabs-adv.html GWT: http://google-web-toolkit.googlecode.com/svn/javadoc/2.0/com/google/gwt/user/client/ui/TabBar.html data table: YUI: http://developer.yahoo.com/yui/datatable/ OpenRico: http://demos.openrico.org/livegrid Ext JS: http://www.extjs.com/deploy/dev/examples/grid/paging.html GWT:http://google-web-toolkit.googlecode.com/svn/javadoc/2.0/com/google/gwt/user/client/ui/Grid.html
26309 | Use JAXB instead of Castor for caGrid serialization | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | Use JAXB instead of Castor for caGrid serialization. Can use COPPA as a reference for how to do this.
28253 | Refactor DAO layer to use generic DAO per domain class pattern | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | Currently we have a base DAO class with some general methods, plus a Search dao with other general methods, and then dao subclasses; but the general methods can be applied to any domain class. As a result often for convenience arbitrary dao subclasses get used for the general methods, making code harder to test. should refactor to use a generic DAO / domain class pattern. e.g. the base Dao interface has genericized methods parameterized by particular domain class type, with subclasses adding more specific methods. this ensures correct usage, making it easier to mock out at higher levels.
28254 | Punt CaArrayDaoFactory and use dependency injection via Guice for all DAOs | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | This will improve testability as dependencies will become more explicit
28255 | Remove static dependencies for SecurityUtils and HibernateUtils; use dependency injection instead | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | this will improve testability
28261 | Use interceptor to do the subsystem entry/exit log messages | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | Right now these are done manually in each method. this is error-prone and pollutes the code. Instead use an Interceptor and do it automatically. Or consider just punting them completely
28655 | Need to convert all static dependencies to use guice dependency injection. | 3 | Tech Stack/Tech Debt | None | 2.5.0 | Code Improvement | this issue was logged as per request from dkokotov via email below in the context of these gforge issues: [#28336] Command-line utility to convert to MAGE-TAB data matrix Copy Number format. [#28346] Command-line utility to convert to MAGE-TAB data matrix Copy Number format - multiple hybs. here is the relevant email text: &quot;...on the caArray side, I would not use Guice Injector the way you are. Just use the right concrete factory implementation class directly - or even the concrete DelimitedFileReader class. And add a issue to the backlog to Guice-ify it later. The goal is to go through the system and Guice-ify all the places where right now we have a static dependency, and this can happen then.&quot;
17754 | Build should copy (replacing existing one) the mysql connector jar in JBOSS's lib directory on deployment | 3 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
17812 | View rendering should be done in a second transaction | 3 | Tech Stack/Tech Debt | To Be Assessed | 2.5.0 | Code Improvement
19854 | Enforce consistent case for CSM table names | 3 | Tech Stack/Tech Debt | To Be Assessed | 2.5.0 | Code Improvement
28248 | upgrade to latest BDA utils. | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Code Improvement | need to upgrade to the latest version of BDA. we are currently on BDA 1.5.9, but 1.6.1 is already out, and 1.7.0 is forthcoming and will probably be out by early may 2010. details can be found here: https://wiki.nci.nih.gov/display/BuildandDeploymentAutomation/BDA+Build+Template+Versions
15618 | Use latest BDA utilities in the build and remove duplication | 3 | Tech Stack/Tech Debt | To Be Assessed | 2.5.0 | Code Improvement
24439 | MageTab parser should create a linear model. | 3 | Tech Stack/Tech Debt | To Be Assessed | 2.5.0 | Defect | The parser should create a one-way chain, without any siblings.
17635 | New caArray-related artifacts in commonlibrary need to have dependencies specified in ivy.xml files. | 3 | Tech Stack/Tech Debt | Analyzed | None | Defect
16436 | Determine support strategy for Firefox 2/3 | 3 | Tech Stack/Tech Debt | To Be Assessed | deferred | Feature Enhancement
26307 | Upgrade CQL processor to one based on a more recent caCORE version | 3 | Tech Stack/Tech Debt | Submitted | 2.5.0 | Feature Enhancement | Improve our implementation of CQL processor by basing it on a more recent version of caCORE / caGrid
20792 | refactor and fix FileAccessServiceBean | 3 | Tech Stack/Tech Debt | None | None | None
24124 | Need to fix all scripts that are referring to old BDA SVN URs after 11/20/2009 changeover. | 3 | Tech Stack/Tech Debt | None | 2.5.0 | Task
25030 | Need to migrate caArray to Anthill Pro 3.x. | 3 | Tech Stack/Tech Debt | None | None | Task | Need to migrate caArray to Anthill Pro 3.x. details: -------- https://wiki.nci.nih.gov/display/BuildandDeploymentAutomation/AntHill+Pro+3.x+Configuration https://wiki.nci.nih.gov/display/BuildandDeploymentAutomation/Anthill+Pro+3+BDA+Requirements
28929 | Elemeents misspelling in caArray error message | 3 | UI | Submitted | None | Defect
15478 | Import option page displayed bottom of the screen. | 3 | UI | Submitted | deferred | Defect
18781 | Incorrect Message | 3 | UI | Submitted | deferred | Defect
24636 | Loading of array Providers never completes when all Assay Types are removed | 3 | UI | Submitted | None | Defect
20343 | Clicking delete button to delete experiment or array design should disable the delete button to prevent double-click-associated errors. | 3 | UI | None | deferred | Feature Enhancement
21236 | [15097] Ability to export displayed table to csv or excel format | 3 | UI | Submitted | deferred | Feature Enhancement
22641 | Loading indicator when My Experiment Workspace exceeds one page | 3 | UI | To Be Assessed | 2.5.0 | Feature Enhancement
22651 | Add Link to edit Experiment Permissions on Experiment Details page | 3 | UI | To Be Assessed | 2.5.0 | Feature Enhancement
22691 | Default sort for Experiment Browse should be reverse chronological order | 3 | UI | Submitted | None | Feature Enhancement | The Browse page has a last updated date column, but the My Experiment Workspace page does not. That column should be added to My Experiment Workspace. Also, both pages should be sorted by last updated date, showing the most recent experiments first.
23432 | &amp;quot;Provider&amp;quot; field is misleading | 3 | UI | Submitted | 2.5.0 | Feature Enhancement
28363 | Add a &quot;Make Public&quot; button to Workspace or Permissions Page | 3 | UI | None | None | Feature Enhancement
13235 | Support protocol applications to raw data files | 3 | UI | Submitted | deferred | New Feature
13361 | Display of scientific symbols | 3 | UI | Submitted | deferred | New Feature
16142 | Make images and styles customizable by local installer. | 3 | UI | Submitted | None | New Feature
28689 | clicking the delete icon for collaboration groups or publications does not ask for confirmation prior to deletion | 3 | UI | Submitted | None | None | Click on Manage Collaboration Groups. For any existing group, clicking on the delete icon will delete that group without confirming that decision with the user. At all other times when this delete-icon behavior is used in caArray a message box is displayed in order to confirm the decision Similar behavior when the delete icon for a publication is clicked.
19367 | Delete button should be gray out user should not have access second time to delete the button | 3 | UI | Submitted | None | None
13665 | Java heap space error when running API CaArraySearchService on DesignElementList | 2 | API | Submitted | None | Defect
28075 | need to generate appropriate UML diagrams describing details of MAGE-TAB processing after respective users guide chapter is completed. | 2 | Documentation | Submitted | 2.5.0 | Documentation Update | after rashmi completes her chapter on MAGE-TAB importing details, the text should be converted into appropriate UML diagrams (e.g., activity diagrams) which should be ultimately uploaded to wiki for reference by dev, qa, and users.
12856 | Configure MySQL to run as service on RHEL, get error on reboot ( avc: denied { append } for pid ) | 2 | Installer | Submitted | None | Defect
13178 | Local installer doesn't successfully shut down jboss; port 31098 is thus still in use and BUILD FAILS | 2 | Installer | Submitted | deferred | Defect
13347 | 2.0.1 Upgrade installer: Interactive Installer 'n' response should return application to previous state | 2 | Installer | Submitted | None | Defect
17901 | caArray upgrade installer should gather as much possible info automatically. | 2 | Installer | Analyzed | deferred | Feature Enhancement
8330 | Expand MageTabParserTest | 2 | Tech Stack/Tech Debt | Submitted | None | Code Improvement
8331 | Expand MageTabTranslatorTest | 2 | Tech Stack/Tech Debt | Submitted | None | Code Improvement
9761 | Move all static text in to resource bundles | 2 | Tech Stack/Tech Debt | Submitted | None | Code Improvement
12282 | Add generic getAll method to SearchDAO, punt individual methods of that form | 2 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
13597 | Hybridization/AbstractBioMaterial.protocolApplications should be one-to-many | 2 | Tech Stack/Tech Debt | Submitted | None | Code Improvement
14580 | Refactor progress bar JS for global use | 2 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
10269 | getIncrementingCopyName needs to bypass filters | 2 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
15620 | Enhance static analysis functionality in caArray build. | 2 | Tech Stack/Tech Debt | Analyzed | deferred | Code Improvement
15635 | Add (and configure in Eclipse) source jars for all main libraries | 2 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
15636 | Use installers for deploying to the tiers | 2 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
16354 | Remove unneeded tags in subversion | 2 | Tech Stack/Tech Debt | None | None | Code Improvement
17627 | Ant complains about &quot;Trying to override old definition of task&quot; | 2 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
17671 | Add support for publishing distributable artifacts to NCI commonlibrary | 2 | Tech Stack/Tech Debt | To Be Assessed | deferred | Code Improvement
18460 | Centralize array design duplicate checking | 2 | Tech Stack/Tech Debt | None | None | Code Improvement
17634 | caArray should use managed connections for authentication/authorization. | 2 | Tech Stack/Tech Debt | None | deferred | Feature Enhancement
10192 | Select associations for annotations ui causes extra whitespace in IE | 2 | UI | Submitted | None | Code Improvement
12664 | Consider removing descriptions from lists of items | 2 | UI | None | deferred | Defect
16630 | Mouse over descriptions for icons are not displayed in Firefox 2.0.0.16 | 2 | UI | Submitted | deferred | Defect
13123 | Display MAGE-TAB Characteristics in the Order provided in the SDRF | 2 | UI | Submitted | deferred | Feature Enhancement
16468 | While Importing the files Upload button function can be disabled | 2 | UI | Submitted | deferred | Feature Enhancement
16353 | Only show array design edit file button if the file can be edited | 2 | UI | To Be Assessed | 2.5.0 | Feature Enhancement
22213 | &quot;Edit File&quot; column in Manage Array Designs should be renamed to &quot;Update File&quot; | 2 | UI | To Be Assessed | deferred | Feature Enhancement
17443 | Create UI for editing of configuration options editable at runtime | 2 | UI | To Be Assessed | deferred | New Feature
14996 | a way to identify owned experiments. | 2 | UI | Submitted | deferred | New Feature
13360 | Implement tab counts consistently across the application | 2 | UI | Submitted | deferred | New Feature
11953 | Recieved out of memory error while searching LogicalProbe object | 1 | API | Analyzed | deferred | Defect
9735 | Use of Affymetrix API requires explicity call to System.gc() (potential performance issue) | 1 | Tech Stack/Tech Debt | Submitted | None | Code Improvement
10213 | Auditable / lastUpdated needed (ProjectDaoImpl.save) | 1 | Tech Stack/Tech Debt | Submitted | None | Code Improvement
15223 | Change text of Validated (Not Parsed) status to Validated (will not be parsed) | 1 | UI | Submitted | deferred | Feature Enhancement