## Risks
ID | Risk | Description | Owner | Impact | Mitigation Plan | Priority | Status | Comments/Resolution
R1 | Short-term solution for the TCGA large data set support was added late to the caArray scope. | The short-term solution to the TCGA data load problem was added late and has impacted the schedule. | Nobody | Medium |  | Medium | Closed | After evaluation and final solution of the data load problem, the schedule for caArray releases has been moved out to accommodate this extra requirement.
R2 | Developer for caIntegrator coming on board late | The second developer for caIntegrator will come on board on October 1 instead of on September 1, 2011 | Rashmi Srinivasa | Medium |  | Medium | Closed | An experienced caBIG developer is on board October 1.
R3 | BDA-Lite requirements adds to scope | The enterprise-mandated BDA-Lite requirement has added to the scope of both caArray and caIntegrator and has impacted the schedule. | JJ Pan | High | Discuss timeline and support from Systems team. | High | Open | The schedule has been extended to accommodate these extra requirements. BDALite has now been implemented on the DEV, QA and STAGE tiers, but not on PRODUCTION yet.
R4 | New CIT policy re: Medium vulnerabilities | The new CIT security policy of mandating resolution of Medium vulnerabilities from app scans will impact the schedule of upcoming releases for caArray and caIntegrator. | JJ Pan | High | Discuss timeline from Systems team. Schedule early preparatory app scans to discover problems earlier. | High | Closed | caArray 2.4.1 and caIntegrator 1.3 addressed these new requirements and were successfully released.
R5 | Significant maintenance and engineering work affect feature development in SOW | Both the caArray and caIntegrator teams are putting a significant amount of effort towards maintenance and engineering activities (like 508 compliance, security issues, tech stack upgrades) now. These are important activities, but they were not listed specifically and may have an impact on the deliverables for the other features listed on SOW | Juli Klemm and Mervi Heiskanen | High | Prioritize requirements with Juli, Mervi and JJ. | High | Closed | The caArray and caIntegrator project plans were adjusted to account for these priorities, and project plan walthroughs were completed in January 2012.
R6 | Retirement of old Ivy and Gforge repositories will result in users being unable to build from source code of older versions of caArray and caIntegrator. | The current release under development (e.g., caArray 2.5.0) has been updated (along with the BDA version it uses - 1.7) to refer to the new repositories. However, older versions (e.g., caArray 2.4.1, 2.4.0. 2.3.1.1, etc.) have not been upgraded in this way. This means that if a user tries to build these older versions from source code, the build will fail. | JJ Pan, Juli Klemm and Mervi Heiskanen | High | Ask the Systems team to resurrect the old Ivy/Gforge repositories in a read-only mode for a few months. | High | Closed | The caArray 2.4.1 source code has been patched to work with the new NCI repositories.
R7 | No support for BDA | Many applications (including caArray and caIntegrator) rely on the BDA jars to do build, deploy and artifact-generation/configuration (e.g., installers/upgraders). With the move to BDALite, several build modifications have been made, and the BDA code has been patched to work with the new NCI/Nexus repositories. However, there is a risk remaining in that these applications still depend on the patched BDA code, and there is no team at the NCI to support that code any more. The best solution would be to rewrite the build and deploy scripts for these applications from scratch, removing all reliance on the BDA code, but this will be time-consuming. | JJ Pan, Juli Klemm and Mervi Heiskanen | High |  | Medium | Open | The risk has been communicated to the NCI, and the current decision is to continue with the reliance on the patched BDA code.
R8 | TRANSCEND architecture decisions will affect scope significantly |  | JJ Pan | High |  | High | Closed | The TRANSCEND architecture has been finalized and the project plan has been updated.
R9 | Coordinated release of caArray, caIntegrator and UPT is needed for tech stack consistency. |  | Rashmi and Shine | Medium |  | Medium | Open | The dependencies among teams is a risk to the schedule of each individual project.
R10 | Availability of sample data files of all types from I-SPY2 for loading into caArray and testing |  | Rashmi and Shine | Medium |  | Medium | Open | We will go ahead with testing of I-SPY1 data, but once the I-SPY2 data is available, we would like to test with those as well.
R11 | Availability of CAS set up on Dev, QA and STAGE tiers for Single Sign-on testing |  | Rashmi and Shine | High |  | High | Open | CAS set-up on the Dev tier is done and testing is ongoing. QA tier has not been set up yet. Latest from Cuong is that the server will be delivered some time between June 15 and June 22, and then the Systems team will have to configure it after that.
R12 | Availability of UCSF personnel for UAT |  | Eve Shalley | Medium |  | Medium | Open
R13 | Availability of new UPT |  | Shine and Rashmi | Medium |  | Medium | Open | caIntegrator and caArray tech stack upgrades will not be completed until the new UPT release is available.
R14 | Resource shortage has affected schedule |  | Rashmi | High |  | High | Closed | Unexpected leaving of developers affected velocity temporarily, but new developers have caught us up.
R15 | Overloading of QA team | Quy is overloaded with multiple projects to test, and is not able to devote sufficient time to test caArray. | Rashmi | High | Release without adequate QA testing. | High | Open | Quy is responsible for testing all caArray featues including the ones for TRANSCEND. His availability is crucial to be able to deliver a quality product.
R16 | Release coordination with API partners | All of caArray's API partners have to upgrade their client jars in order to work with the new caArray 2.5.0. This means that their release schedules need to be coordinated with caArray's. | Rashmi | Medium | Release caArray 2.5.0 for local installers in July, but don't upgrade the NCI Production caArray tier to 2.5.0 until partners are ready in August. | Medium | Open | Rembrandt is testing now. As of June 12, GenePattern does not have the time to test yet, and caB2B has not started testing either.
R17 | Old tech stack in caIntegrator prevents EJB-layer SSO from working | caIntegrator uses Acegi security, and this feature seems to require an upgrade of the security framework to Spring security. | Shine and Rashmi | Medium | If the issue is not resolved by the end of June 8, a strategy would be to release with Single Sign-on working in only the web application layer (linking to a caArray experiment from caIntegrator, and navigating between the 2 applications in a web browser). | Medium | Open | caIntegrator uses Acegi security, and this feature seems to require an upgrade of the security framework to Spring security. This is a major undertaking, and will have to be deferred until after release v1.4. The team has shifted focus to bug fixes. Note that there is no major impact to the user: * Single Sign-on still works for the major use case - a user can navigate between the caIntegrator and caArray web applications without having to type in credentials again. This is 90% of the use case. * The only place where the user cannot take advantage of SSO is when a caIntegrator Study Manager first sets up a study and adds a genomic data source. He/she will have to type in their credentials at this point, similar to how it works today.