## Action_Items
Item # | Description | Responsible Party | Date Identified | Disposition
1 | Set up a meeting to discuss alternative short-term solutions to the large data set import problem. | Rashmi Srinivasa | 2011-08-04 | Complete
2 | Send requirements process to JJ and schedule follow-up meeting. | Rashmi Srinivasa | 2011-08-04 | Complete
3 | Provide a list of TCGA data - loadable/not loadable/unknowns and some options | Shine Jacob | 2011-08-04 | Complete
4 | Set up a meeting to discuss which TCGA data types need to be loaded into caIntegrator. Attendees: Tanya Davidson, Xiaopeng, Juli, Mervi, Shine, JP. (Mervi, Shine and JP all have vacation plans during August.) | Mervi Heiskanen | 2011-08-04 | Complete
5 | Set up a meeting to discuss caGrid 1.2 upgrade | Shine Jacob | 2011-08-04 | Complete
6 | Set up a meeting to discuss access needs to run caArrayImporter client to load data onto caArray on NCI Production server. | JJ Pan | 2011-08-16 | Complete
7 | Write up a short capability description of caArrayImporter client and QTP for loading large data sets. Quy and Andrew to support. | Rashmi Srinivasa | 2011-08-16 | Complete
8 | Write up a requirement for autoloader – short term solution using caArrayImporter or QTP. Xiaopang to provide input. | Rashmi Srinivasa | 2011-08-16 | Complete
9 | Follow up with Rashmi to see if she can help resolve the problem of running the 508 compliance testing tool against caIntegrator. | Quy Phung | 2011-08-16 | Complete
10 | Tony Kervalage needs list of TRANSCEND requirements and LOE. | Eve Shalley | 2011-08-16 | Complete
11 | Shine and Rashmi to provide latest product roadmaps to Zhong for the MAT-KC. | Shine Jacob and Rashmi Srinivasa | 2011-08-23 | Complete
12 | Provide TRANSCEND requirements document to JJ. | Shine Jacob | 2011-08-30 | Complete
13 | caArray and caIntegrator demos for JJ | Rashmi Srinivasa and Shine Jacob | 2011-09-06 | Complete
14 | Talk to the UPT team re: dissuading caArray users from creating groups within UPT. | JJ Pan and Larry Brem | 2011-09-06 | Complete
15 | Follow up with Doug Hosier on BDA-Lite and AntHill Pro 3.0 requirement. | JJ Pan | 2011-09-20 | Complete
16 | Follow up on CIT Security policy change re: resolution of Medium vulnerabilities of app scan. | JJ Pan | 2011-09-20 | Complete
17 | Upgrade Training tier to caArray 2.4.1. | Don Swan | 2011-10-18 | Complete
18 | Upgrade Curation tier to caArray 2.4.1. | Quy Phung | 2011-10-18 | Complete
19 | Create wireframes to depict how permissions will work across caIntegrator and caArray. | Andy Evans and Will Fitzhugh | 2011-10-18 | Complete
20 | Work with Eve to schedule a meeting with UCSF. | Juli Klemm | 2011-11-15 | Complete
21 | Links to the caArray User’s Guide on the Download Center -> Download page are incorrect | Rashmi Srinivasa | 2011-11-15 | Complete
22 | Create sample experiments in caArray to represent TRANSCEND use cases. | Maureen Colbert | 2011-11-15 | Complete
23 | Update permissions wireframes for TRANSCEND to reflect the latest understanding of the data. | Andy Evans | 2011-11-15 | Complete
24 | Set up regular once-in-2-weeks meetings with TRANSCEND | Eve Shalley | 2011-11-30 | Complete
25 | Set up a meeting with the caDSR team to discuss permissible values. | Mervi Heiskanen | 2011-12-06 | Complete
26 | Set up an internal meeting to evaluate alternative approaches to setting permissions (common UI versus changes to individual apps) | Rashmi Srinivasa | 2011-12-06 | Complete
27 | Get sample data files from Sarah Davis/TRANSCEND team. | Eve Shalley | 2012-01-24 | Complete
28 | Make the following changes to the caArray project plan: * Add a task to re-run the Section 508 compliance scan for 2.5.0 to ensure we are above 90%. * Move the API integration partner testing effort up to Beta 1. * Give the final release announcement task 2 weeks of lead time for getting approval. | Rashmi Srinivasa | 2012-01-24 | Complete
29 | Put in a request for the caArray and caIntegrator QA-VM tiers to request additional heap space (8GB for the application server). | Jacob Mensah | 2012-01-31 | Complete
30 | Schedule meeting to discuss TRANSCEND architecture recommendations and effect on caArray and caIntegrator project plans. | Rashmi Srinivasa | 2012-01-31 | Complete
31 | Send the Agilent 415K ADF custom array design to Zhong. | Henry Schaefer | 2012-02-14 | Complete
32 | Send triaged bug list to Juli, JJ, Deb and Larry and schedule a second Bug Triage meeting. | Rashmi Srinivasa | 2012-02-21 | Complete
33 | Submit ticket for BDALite configuration on the new STAGE tier | Rashmi Srinivasa | 2012-02-21 | Complete
34 | Discuss need for disaster recovery / backup server solution | Juli Klemm and JJ Pan | 2012-02-28 | Complete
35 | Forward information re: dependency on EVS | Mervi Heiskanen | 2012-02-28 | Complete
36 | Warn caArray community re: planned down time of <1 hour on Thursday at 8am. | Juli Klemm and Zhong Li | 2012-03-06 | Complete
37 | Get modify access to Jira for Jill. | Rashmi Srinivasa | 2012-03-06 | Complete
38 | Answer MAGE-TAB export question sent to App Support | Rashmi Srinivasa | 2012-03-27 | Complete
39 | Send a note to the caArray community about the 2.4.1 bug. | Juli Klemm | 2012-04-10 | Complete (Not required)
40 | Check with Matt Kennedy and Eve re: getting hardware requirements to UCSF | Rashmi Srinivasa | 2012-04-17 | Complete
41 | Check with Eve re: bringing back the risk related to unavailability of I-SPY2 data | Rashmi Srinivasa | 2012-04-17 | Complete (TRANSCEND-127 is open.)
42 | Schedule follow-up meeting re: caGrid upgrade with Todd, Larry, JJ and Deb. | Rashmi Srinivasa | 2012-05-08 | Complete
43 | Send information to Mervi about user/lab who is installing caIntegrator. | Don Swan | 2012-05-08 | Complete
44 | Talk to Sudha re: QA backup during Quy’s absence in the end of July. | Quy Phung and Rashmi Srinivasa | 2012-05-15 | Complete
45 | Send TRANSCEND Use Cases document to JJ and Deb. | Rashmi Srinivasa | 2012-05-22 | Complete
46 | Confirm with Jill regarding the documentation updates for caArray. | Rashmi Srinivasa | 2012-05-29 | Complete
47 | Review Test Plan for SSO and Non-SSO. | Quy Phung and Henry Schaefer | 2012-05-29 | Complete
48 | Send caIntegrator bug estimates to JJ and Mervi | Shine | 2012-06-14 | Complete
49 | Send NCI-Frederick caIntegrator user contact info to Larry Brem. | Don Swan | 2012-06-14 | Complete
50 | Follow up with Systems team re: file storage for the caArray Production tier. | JJ Pan | 2012-07-10 | Complete
51 | Submit tickets to get the Curation and Training tiers upgraded to AHP3 and the new tech stack. | Rashmi Srinivasa | 2012-07-24 | Complete
52 | Submit tickets to decommission the old caArray and caIntegrator tiers. | Rashmi Srinivasa | 2012-07-24 | Complete
53 | Upgrade caArray Curation tier. | Jacob Mensah | 2012-07-24 | Complete
54 | Upgrade caArray Training tier. | Jacob Mensah | 2012-07-24 | Complete
55 | Upgrade caIntegrator Training tier. | Cuong Nguyen | 2012-07-24 | Complete
56 | Request more disk space on caArray PRODUCTION | Rashmi Srinivasa | 2012-09-11 | Complete
57 | Test caArray database replication by putting a backup on the STAGE tier | Yeon Choi | 2012-10-02 | Complete
58 | Checklist for OSDI Kickoff | Rashmi Srinivasa and Shine Jacob | 2013-01-04 | Complete
59 | Include CSM/UPT upgrade and Section 508 compliance on project plan | Rashmi Srinivasa and Shine Jacob | 2013-01-04 | Complete
60 | Rewrite PMP in EPLC format | Rashmi Srinivasa and Shine Jacob | 2013-01-04 | Complete
61 | Shady Grove move orientation | Full Team | 2013-01-09 | Complete
62 | Discuss caArray Data Migration to File System | JJ Pan (with Juli Klemm and Yeon Choi) | 2013-01-08 | Complete
63 | Work with QA and Systems teams on estimates/project plan. | Rashmi Srinivasa and Shine Jacob | 2013-01-08 | Complete
64 | TRANSCEND Support (caIntegrator Jboss problems and caArray usage questions) | Abe Evans-EL and Rashmi Srinivasa | 2013-01-08 | Complete
65 | Contact previous authors and find out if they need any private branches retained in GitHub | Sree Nampally and Larry Brem | 2013-01-15 | Complete
66 | Look into changing names from caArray2/caIntegrator2 to caArray/caIntegrator | Winston Cheng and Abe Evans-EL | 2013-01-15 | Complete
67 | Put in a request to Clint's team to archive caintegrator-info.nci.nih.gov | Ulrike Wagner | 2013-01-15 | Complete
68 | Look into context-sensitive help links in caIntegrator | Shine Jacob and Abe Evans-EL | 2013-01-15 | Complete
69 | Contact Tabitha re: a possible walkthrough/demo of caIntegrator | Rashmi Srinivasa | 2013-01-15 | Complete
70 | Support from System team for OSDI | Juli Klemm |  | Complete
71 | Options to make 100% 508 compliance for caIntegrator without code changes | Shine Jacob and Abe Evans-EL |  | Complete
72 | Follow up with Kevin Burns on Agendia (Tina's) request for a caArray account. They already have guest credentials to the STAGE tier. | Brian Hughes | 2013-01-29 | Complete
73 | Update QA projections and Deployment schedule | Rashmi Srinivasa | 2013-02-05 | Complete
74 | Follow up with Sudha and Sichen to get approval to deploy the latest caArray tag to STAGE in order to test the AntHill Pro setup for OSDI. | Marina and JJ | 2013-03-19 | Complete
75 | Request caIntegrator QA tier appscan. | Shine Jacob | 2013-04-02 | Complete
76 | Request caArray QA tier appscan. | Mike Hunter and Rashmi Srinivasa | 2013-04-02 | Complete
77 | Request gitHub integration with AntHill Pro on caArray PRODUCTION tier. | Mike Hunter | 2013-04-09 | Complete
78 | Get back to Brian Hughes about the mouse astrocytoma study in caIntegrator | Shine Jacob | 2013-04-23 | Complete
79 | Work with Systems to resolve the UPT-caIntegrator issues Marina reported | Abe Evans-El | 2013-04-23 | Complete
80 | Request gitHub integration with AntHill Pro on caIntegrator PRODUCTION tier. | Abe Evans-El | 2013-04-23 | Complete
81 | Confirm that all caArray tiers now have gitHub integration with AntHill Pro configured. | Mike Hunter | 2013-05-07 | Complete
82 | Hold a meeting with Jacob Shine, Juli Klemm, Ulli Wagner, and JJ Pan to plan the caArray 2.5.2 release and the caIntegrator 1.4.2 release. | Mike Hunter | 2013-05-14 | Complete
83 | Run Section 508 scan on caIntegrator QA tier. | Mike Hunter | 2013-05-14 | Complete
84 | Follow up with Sarah Elkins on the status of updating AHP on caArray STAGE and TRAINING to use GitHub. | Mike Hunter | 2013-05-14 | Complete
85 | Contact Eva Shalley to find out if TRANSCEND plans to upgrade to the next release of caIntegrator. | Mike Hunter | 2013-05-14 | Complete - combined with 88
86 | Invite Laxmi Lolla or Ye Wu to attend an upcoming status meeting to share her feedback and recommendations regarding usability and performance. | Ulrike Wagner | 2013-05-14 | Complete
87 | Clean up the backlog of issues in Jira for caIntegrator. | Mervi Heiskanen, Shine Jacob | 2013-05-21 | Complete
88 | Schedule meeting with Eve and Tabitha to discuss performance and usability. | Mike Hunter | 2013-05-28 | Complete
89 | Provide links to the MAT KC videos related to data submission. | Jill Hadfield | 2013-05-28 | Complete
90 | Review the MAT KC videos related to data submission (links provided by Jill). | Mike Hunter | 2013-05-28 | Complete
91 | Provide Eve Shalley a summary of the changes in the next releases of caArray and caIntegrator | Mike Hunter | 2013-05-30 | Complete
92 | Discuss the documentation update process | Mike Hunter and Jill Hadfield | 2013-06-04 | Complete
93 | Find the past FISMA documentation and confirm the tracker issues | Mike Hunter | 2013-06-04 | Complete
94 | Add a %FTE ("Work") column to the project plans and populate it going forward | Mike Hunter and Shine Jacob | 2013-06-04 | Complete
95 | Assess how upgrading UPT for caArray might impact TRANSCEND (any SSO user running different versions of UPT). | Mike Hunter, Winston Cheng, and Abe Evans-El | 2013-06-11 | Complete
96 | Follow up with Yeon to confirm that we can continue with our current backup strategy for caArray (impacts move to file system) | Mike Hunter | 2013-06-11 | Complete
97 | Provide JJ the purpose and agenda for our meeting with Verifying Group (RE FISMA). | Mike Hunter | 2013-06-11 | Complete
98 | Schedule a meeting with Craig Hayn from the Verifying Group to confirm our plan for addressing the FISMA items meets the spirit of the POAM. | JJ Pan | 2013-06-11 | Complete
99 | Find out when UPT 5.0 will be officially released and required on the tech stack. | JJ Pan | 2013-06-18 | Assigned
100 | Create/update the test plan for testing the restore of caArray data from tape backup. | Mike Hunter, Marina Omelchenko, Winston Cheng | 2013-06-18 | Complete
101 | Send target release target dates to Ulli to communicate to Engineering | Mike Hunter | 2013-06-25 | Complete
102 | Post the caIntegrator screencasts to a private wiki (need the files) | Shine Jacob, Abe Evans-EL, Ulrike Wagner | 2013-06-25 | Complete
103 | In August, invite AIM team and IVIM to discuss upgrade path for caIntegrator. | Ulrike Wagner | 2013-06-25 | Assigned
104 | Invite NBIA team to discuss upgrade path for caIntegrator. | Abe Evans-El and Mike Hunter | 2013-06-25 | Assigned
105 | Send out the caArray audit log info so that the team can consider how to conduct the review. | Mike Hunter | 2013-07-09 | Complete
106 | Determine how to conduct the caArray audit log reviews. | Mike Hunter, JJ Pan, Juli Klemm, Winston Cheng | 2013-07-09 | Complete
107 | Follow up on the versioning guidance for caIntegrator (1.5 vs 1.4.2). | JJ Pan | 2013-07-09 | Complete
108 | Provide Juli the nature of the verbiage for making an experiment public. | Mike Hunter | 2013-07-16 | Complete
109 | Provide the verbiage for making an experiment public and get it approved by Legal. | Juli Klemm | 2013-07-16 | In Progress
110 | Respond to JJ's email about audit log review procedure. | Mike Hunter | 2013-07-16 | Complete
111 | Review caArray audit log capabilities in the 7/30 status meeting. | Mike Hunter and Winston Cheng | 2013-07-16 | Assigned
112 | Review caIntegrator performance improvements in the 7/23 status meeting. | Mike Hunter and Abe Evans-El | 2013-07-16 | Complete
113 | Review the project plans for caArray and caIntegrator to determine if there are things to do to streamline getting both applications back into Production before September | JJ Pan | 2013-07-23 | Complete
114 | Decide which of the three options proposed for making it easy to review audit log entries each month to implement | JJ Pan and Juli Klemm | 2013-07-23 | Complete
115 | After Abe addresses the performance drop for Agilent Data Sets, share Abe's performance page from the wiki with Eve Shalley | Mike Hunter | 2013-07-23 | Assigned
116
117
118
119
120
121