## Risks
ID | Risk | Owner | Impact | Status | Resolution/Mitigation
R1 | Short-term solution for the TCGA large data set support was added late to the caArray scope. | Nobody | Medium | Closed | After evaluation and final solution of the data load problem, the schedule for caArray releases has been moved out to accommodate this extra requirement.
R2 | Developer for caIntegrator coming on board late | Rashmi Srinivasa | Medium | Closed | An experienced caBIG developer is on board October 1.
R3 | BDA-Lite requirements adds to scope | JJ Pan | High | Closed | The schedule has been extended to accommodate these extra requirements. BDALite has now been implemented on all tiers.
R4 | New CIT policy re: Medium vulnerabilities | JJ Pan | High | Closed | caArray 2.4.1 and caIntegrator 1.3 addressed these new requirements and were successfully released.
R5 | Significant maintenance and engineering work affect feature development in SOW | Juli Klemm and Mervi Heiskanen | High | Closed | The caArray and caIntegrator project plans were adjusted to account for these priorities, and project plan walkthroughs were completed in January 2012.
R6 | Retirement of old Ivy and Gforge repositories will result in users being unable to build from source code of older versions of caArray and caIntegrator. | JJ Pan, Juli Klemm and Mervi Heiskanen | High | Closed | The caArray 2.4.1 source code has been patched to work with the new NCI repositories.
R7 | No support for BDA | JJ Pan, Juli Klemm and Mervi Heiskanen | Medium | Open | The risk has been communicated to the NCI, and the current decision is to continue with the reliance on the patched BDA code.
R8 | TRANSCEND architecture decisions will affect scope significantly | JJ Pan | High | Closed | The TRANSCEND architecture has been finalized and the project plan has been updated.
R9 | Coordinated release of caArray, caIntegrator and UPT is needed for tech stack consistency. | Rashmi and Shine | Medium | Closed | All released.
R10 | Availability of sample data files of all types from I-SPY2 for loading into caArray and testing | Eve Shalley | Medium | Open | We will go ahead with testing of I-SPY1 data, but once the I-SPY2 data is available, we would like to test with that as well.
R11 | Availability of CAS set up on Dev, QA and STAGE tiers for Single Sign-on testing | Rashmi and Shine | High | Closed
R12 | Availability of UCSF personnel for UAT | Eve Shalley | Low | Closed | We have provided several drops to UCSF for UAT, but they have not had the time to test and provide feedback yet.
R13 | Availability of new UPT | Shine and Rashmi | Medium | Closed | caIntegrator and caArray have completed this upgrade.
R14 | Resource shortage has affected schedule | Rashmi and Shine | High | Closed | Unexpected leaving of developers affected velocity temporarily, but new developers have caught us up.
R15 | Overloading of QA team | Rashmi | Medium | Closed | Quy is not fully available due to PTO and other project responsibilities.
R16 | Release coordination with caArray API partners | Rashmi | Medium | Closed
R17 | Old tech stack in caIntegrator prevents EJB-layer SSO from working | Shine and Rashmi | Medium | Closed | caIntegrator uses Acegi security, and this feature seems to require an upgrade of the security framework to Spring security. This is a major undertaking, and has been deferred until after release v1.4. The team has shifted focus to bug fixes
R18 | QA team staffing change leads to knowledge loss and incomplete testing | Rashmi | Medium | Open | A new QA team member has taken over as of August 27. Since there was no overlap between the old QA person and the new one, loss of knowledge can lead to incomplete testing of the product.
R19 | Small size of teams leading to slow progress | Deb Hope | High | Closed | Budget limitations have reduced the team size to half a developer for each of the two applications, and progress is slow. Effective resolution of issues requires a bigger team size.
R20 | After OSDI migration to GitHub, code cannot be tested on NCI tiers due to the AntHill Pro updates being on hold | Juli, JJ and Doug Hosier | High | Open | Updating AHP builds is on hold due to ongoing discussions among Juli, JJ and Doug Hosier about Systems team support. This is a risk since future code changes will happen on GitHub and we will not be able to test on the Dev/QA tiers. (The QA team is scheduled to start regression testing the next release on the QA tier on March 12.)