## Action_Items
Item # | Description | Responsible Party | Date Identified | Disposition
1 | Set up a meeting to discuss alternative short-term solutions to the large data set import problem. | Rashmi Srinivasa | 2011-08-04 | Complete
2 | Send requirements process to JJ and schedule follow-up meeting. | Rashmi Srinivasa | 2011-08-04 | Complete
3 | Provide a list of TCGA data - loadable/not loadable/unknowns and some options | Shine Jacob | 2011-08-04 | Complete
4 | Set up a meeting to discuss which TCGA data types need to be loaded into caIntegrator. Attendees: Tanya Davidson, Xiaopeng, Juli, Mervi, Shine, JP. (Mervi, Shine and JP all have vacation plans during August.) | Mervi Heiskanen | 2011-08-04 | Complete
5 | Set up a meeting to discuss caGrid 1.2 upgrade | Shine Jacob | 2011-08-04 | On Hold
6 | Set up a meeting to discuss access needs to run caArrayImporter client to load data onto caArray on NCI Production server. | JJ Pan | 2011-08-16 | Complete
7 | Write up a short capability description of caArrayImporter client and QTP for loading large data sets. Quy and Andrew to support. | Rashmi Srinivasa | 2011-08-16 | Complete
8 | Write up a requirement for autoloader – short term solution using caArrayImporter or QTP. Xiaopang to provide input. | Rashmi Srinivasa | 2011-08-16 | Complete
9 | Follow up with Rashmi to see if she can help resolve the problem of running the 508 compliance testing tool against caIntegrator. | Quy Phung | 2011-08-16 | Complete
10 | Tony Kervalage needs list of TRANSCEND requirements and LOE. | Eve Shalley | 2011-08-16 | Complete
11 | Shine and Rashmi to provide latest product roadmaps to Zhong for the MAT-KC. | Shine Jacob and Rashmi Srinivasa | 2011-08-23 | Complete
12 | Provide TRANSCEND requirements document to JJ. | Shine Jacob | 2011-08-30 | Complete
13 | caArray and caIntegrator demos for JJ | Rashmi Srinivasa and Shine Jacob | 2011-09-06 | Complete
14 | Talk to the UPT team re: dissuading caArray users from creating groups within UPT. | JJ Pan and Larry Brem | 2011-09-06 | Complete
15 | Follow up with Doug Hosier on BDA-Lite and AntHill Pro 3.0 requirement. | JJ Pan | 2011-09-20 | Complete
16 | Follow up on CIT Security policy change re: resolution of Medium vulnerabilities of app scan. | JJ Pan | 2011-09-20 | Complete
17 | Upgrade Training tier to caArray 2.4.1. | Don Swan | 2011-10-18 | Complete
18 | Upgrade Curation tier to caArray 2.4.1. | Quy Phung | 2011-10-18 | Complete
19 | Create wireframes to depict how permissions will work across caIntegrator and caArray. | Andy Evans and Will Fitzhugh | 2011-10-18 | Complete
20 | Work with Eve to schedule a meeting with UCSF. | Juli Klemm | 2011-11-15 | Complete
21 | Links to the caArray User’s Guide on the Download Center -> Download page are incorrect | Rashmi Srinivasa | 2011-11-15 | Complete
22 | Create sample experiments in caArray to represent TRANSCEND use cases. | Maureen Colbert | 2011-11-15 | Complete
23 | Update permissions wireframes for TRANSCEND to reflect the latest understanding of the data. | Andy Evans | 2011-11-15 | Complete
24 | Set up regular once-in-2-weeks meetings with TRANSCEND | Eve Shalley | 2011-11-30 | Complete
25 | Set up a meeting with the caDSR team to discuss permissible values. | Mervi Heiskanen | 2011-12-06 | Complete
26 | Set up an internal meeting to evaluate alternative approaches to setting permissions (common UI versus changes to individual apps) | Rashmi Srinivasa | 2011-12-06 | Complete
27 | Get sample data files from Sarah Davis/TRANSCEND team. | Deb Hope to ping Eve Shalley | 2012-01-24 | On Hold (I-SPY2 data not yet available)
28 | Make the following changes to the caArray project plan: * Add a task to re-run the Section 508 compliance scan for 2.5.0 to ensure we are above 90%. * Move the API integration partner testing effort up to Beta 1. * Give the final release announcement task 2 weeks of lead time for getting approval. | Rashmi Srinivasa | 2012-01-24 | Complete
29 | Put in a request for the caArray and caIntegrator QA-VM tiers to request additional heap space (8GB for the application server). | Jacob Mensah | 2012-01-31 | Complete
30 | Schedule meeting to discuss TRANSCEND architecture recommendations and effect on caArray and caIntegrator project plans. | Rashmi Srinivasa | 2012-01-31 | Complete
31 | Send the Agilent 415K ADF custom array design to Zhong. | Henry Schaefer | 2012-02-14 | Complete
32 | Send triaged bug list to Juli, JJ, Deb and Larry and schedule a second Bug Triage meeting. | Rashmi Srinivasa | 2012-02-21 | Complete
33 | Submit ticket for BDALite configuration on the new STAGE tier | Rashmi Srinivasa | 2012-02-21 | Complete
34 | Discuss need for disaster recovery / backup server solution | Juli Klemm and JJ Pan | 2012-02-28 | Complete
35 | Forward information re: dependency on EVS | Mervi Heiskanen | 2012-02-28 | Complete
36 | Warn caArray community re: planned down time of <1 hour on Thursday at 8am. | Juli Klemm and Zhong Li | 2012-03-06 | In Progress
37 | Get modify access to Jira for Jill. | Rashmi Srinivasa | 2012-03-06 | Not Started