## Risks
ID | Risk | Owner | Impact | Status | Resolution/Mitigation
R1 | Short-term solution for the TCGA large data set support was added late to the caArray scope. | Nobody | Medium | Closed | After evaluation and final solution of the data load problem, the schedule for caArray releases has been moved out to accommodate this extra requirement.
R2 | Developer for caIntegrator coming on board late | Rashmi Srinivasa | Medium | Closed | An experienced caBIG developer is on board October 1.
R3 | BDA-Lite requirements adds to scope | JJ Pan | High | Closed | The schedule has been extended to accommodate these extra requirements. BDALite has now been implemented on all tiers.
R4 | New CIT policy re: Medium vulnerabilities | JJ Pan | High | Closed | caArray 2.4.1 and caIntegrator 1.3 addressed these new requirements and were successfully released.
R5 | Significant maintenance and engineering work affect feature development in SOW | Juli Klemm and Mervi Heiskanen | High | Closed | The caArray and caIntegrator project plans were adjusted to account for these priorities, and project plan walkthroughs were completed in January 2012.
R6 | Retirement of old Ivy and Gforge repositories will result in users being unable to build from source code of older versions of caArray and caIntegrator. | JJ Pan, Juli Klemm and Mervi Heiskanen | High | Closed | The caArray 2.4.1 source code has been patched to work with the new NCI repositories.
R7 | No support for BDA | JJ Pan, Juli Klemm and Mervi Heiskanen | Medium | Open | The risk has been communicated to the NCI, and the current decision is to continue with the reliance on the patched BDA code.
R8 | TRANSCEND architecture decisions will affect scope significantly | JJ Pan | High | Closed | The TRANSCEND architecture has been finalized and the project plan has been updated.
R9 | Coordinated release of caArray, caIntegrator and UPT is needed for tech stack consistency. | Rashmi and Shine | Medium | Closed | All released.
R10 | Availability of sample data files of all types from I-SPY2 for loading into caArray and testing | Rashmi and Shine | Medium | Open | We will go ahead with testing of I-SPY1 data, but once the I-SPY2 data is available, we would like to test with that as well.
R11 | Availability of CAS set up on Dev, QA and STAGE tiers for Single Sign-on testing | Rashmi and Shine | High | Closed
R12 | Availability of UCSF personnel for UAT | Eve Shalley | Low | Open | We have provided several drops to UCSF for UAT, but they have not had the time to test and provide feedback yet.
R13 | Availability of new UPT | Shine and Rashmi | Medium | Closed | caIntegrator and caArray have completed this upgrade.
R14 | Resource shortage has affected schedule | Rashmi and Shine | High | Closed | Unexpected leaving of developers affected velocity temporarily, but new developers have caught us up.
R15 | Overloading of QA team | Rashmi | Medium | Open | Quy is not fully available due to PTO and other project responsibilities.
R16 | Release coordination with caArray API partners | Rashmi | Medium | Closed
R17 | Old tech stack in caIntegrator prevents EJB-layer SSO from working | Shine and Rashmi | Medium | Closed | caIntegrator uses Acegi security, and this feature seems to require an upgrade of the security framework to Spring security. This is a major undertaking, and has been deferred until after release v1.4. The team has shifted focus to bug fixes