# caArray-caIntegrator – Status Meeting Minutes

**January 31, 2012**

## Attendees:

|  |  |  |  |
| --- | --- | --- | --- |
| Andy Evans |  | Mervi Heiskanen |  |
| Cuong Nguyen |  | Michael Benham |  |
| Deb Hope |  | Quy Phung |  |
| Don Swan |  | Rashmi Srinivasa |  |
| Eve Shalley |  | Robert Shirley |  |
| Henry Schaefer |  | Shine Jacob |  |
| Jacob Mensah |  | Tony Kerlavage |  |
| Jill Hadfield |  | Will Fitzhugh |  |
| JJ Pan |  | Xiaopeng Bian |  |
| JP Marple |  | Yeon Choi |  |
| Juli Klemm |  | Zhong Li |  |
| Larry Brem |  | Greg Gurley |  |
| Maki Duncan |  |  |  |

## Discussion:

### caArray:

* caArray 2.5.0 status:
  + Enterprise architecture solution for TRANSCEND security:
    - Santosh’s team recommended a simple approach – CAS without Grid security for Single Sign-on, and separate role/access provisioning in caArray and caIntegrator.
    - Awaiting formal recommendation and decision from NCI before proceeding – timeframe to be discussed at this meeting.
  + Iteration M21 is Complete, and M22 is In Progress.
    - Splitting Imports – the “happy path” is complete. Handling failures is in progress.
    - Improved Uploads – prototype shows that jquery approach satisfies the file size requirements, but now prototyping fallback to a different method to fully support IE browsers. ACTION: Schedule meeting with Arch. Review Board after fallback has been prototyped.
  + BDALite: AHP3 track setup on the Dev and QA-VM tiers is complete.
    - Meeting with Systems team on Wednesday to discuss additional improvements.
  + Other:
    - UPT team demo-ed configurability to prevent caArray users from unintentionally creating groups. Our plan to test and integrate remains unchanged: ARRAY-2258 and ARRAY-2259.
    - Disappearing experiments after PROD-to-STAGE database copy problem (ARRAY-2214): Resolved.
    - Experiment inconsistency between Curation and PROD (ARRAY-2231): In Progress.
    - Problems building from 2.4.x source (ARRAY-2230): Ongoing discussion with JJ and Doug Hosier.
* Project plan: <https://ncisvn.nci.nih.gov/svn/caarray2/trunk/docs/project_management/caArray_Project_Plan.mpp>

### caIntegrator:

* Tech Stack Upgrade – In Progress.
  + QA tier - CAINT-1096 – Errors associated with file system after new build
  + UPT upgrade and caDSR
* Other activities
  + Xenoline update: On Hold until their team responds.
  + Release in April?
  + Other maintenance and bug fixes.
  + TRANSCEND – see below
* Updated project plan is here, and there will be a walkthrough at next week’s status meeting: [https://ncisvn.nci.nih.gov/svn/caintegrator2/trunk/docs/project\_management/caintegrator\_project\_plan.mpp](https://ncisvn.nci.nih.gov/svn/caintegrator2/trunk/docs/project_management/caintegrator_project_plan.mpp" \t "_blank)

### TRANSCEND:

* Enterprise architecture solution for TRANSCEND security:
  + Santosh’s team recommended a simple approach – CAS without Grid security for Single Sign-on, and separate role/access provisioning in caArray and caIntegrator.
  + Awaiting formal recommendation and decision from NCI before proceeding – timeframe to be discussed at this meeting.
* Waiting for sample data files from TRANSCEND (Deb -> Eve -> Sarah Davis).
* Study Archive – Ongoing
* Today’s TRANSCEND technology meeting cancelled.

### Systems and DBA:

* STAGE and PRODUCTION tiers for caArray and caIntegrator – Approved. No definite date yet for when the servers will be provisioned and ready.

### Documentation:

* No updates this week.

### Support and Knowledge Center:

* No updates this week.

## Open Action Items:

* Full list of closed and current action items are available here: <https://ncisvn.nci.nih.gov/svn/caarray2/trunk/docs/project_management/caArray_caIntegrator_Action_Items.xlsx>

| **Item #** | **Description** | **Responsible Party** | **Date Identified** | **Disposition** |
| --- | --- | --- | --- | --- |
| 14. | Talk to the UPT team re: preventing caArray users from creating groups within UPT. | JJ Pan and Larry Brem | 9/6/2011 | Complete (UPT team has just finished implementing it in 4.2.3, and is in the process of QA-testing it) |
| 27. | Get sample data files from Sarah Davis/TRANSCEND team. | Deb Hope to ping Eve Shalley | 1/24/2012 | Not Started |
| 28. | Make the following changes to the caArray project plan:  \* Add a task to re-run the Section 508 compliance scan for 2.5.0 to ensure we are above 90%.  \* Move the API integration partner testing effort up to Beta 1.  \* Give the final release announcement task 2 weeks of lead time for getting approval.  \* Schedule a meeting with the Architecture Review Board after technology selection for Improved Upload. | Rashmi Srinivasa | 1/24/2012 | Complete |