# caArray-caIntegrator – Status Meeting

**April 24, 2012**

## Attendees:

|  |  |  |  |
| --- | --- | --- | --- |
| Cuong Nguyen | Y | Mervi Heiskanen |  |
| Deb Hope | Y | Michael Benham |  |
| Don Swan | Y | Paul Shrabstein | Y |
| Eve Shalley |  | Quy Phung | Y |
| Greg Gurley | Y | Rashmi Srinivasa | Y |
| Hemant Undale |  | Robert Shirley |  |
| Henry Schaefer | Y | Shine Jacob |  |
| Jacob Mensah | Y | Tony Kerlavage |  |
| Jill Hadfield |  | Will Fitzhugh |  |
| JJ Pan | Y | Xiaopeng Bian | Y |
| JP Marple | Y | Yeon Choi |  |
| Juli Klemm | Y | Zhong Li |  |
| Larry Brem | Y |  |  |

## Discussion:

### caArray:

* caArray status:
  + TRANSCEND (see detailed status in the TRANSCEND section):
    - Permissions by Treatment Arm – Demo-ed to UCSF. On STAGE and ready for UAT.
    - Auto Refresh – Complete. Integration testing with caIntegrator.
    - Single Sign-on – Major development on the caArray side Complete, and developer has started implementing SSO on caIntegrator. Minor navigation and look-and-feel issues will be tackled after integration testing between the 2 applications.
  + Tech Stack:
    - caGrid upgrade – Promising progress on caGrid v1.5 upgrade. Gathered estimates in support of decision on whether to move forward. Discussion at the end of this meeting.
  + API partner integration testing: In Progress. (caIntegrator, Rembrandt and geWorkbench testing now. GenePattern will test after next month’s release.)
  + Curation issues:
    - Slow parsing of Copy Number Data Matrix files and Reparse issue are on the 2.5.0 backlog now.
* Project plan: <https://ncisvn.nci.nih.gov/svn/caarray2/trunk/docs/project_management/caArray_Project_Plan.mpp>

### caIntegrator:

* Tech Stack Upgrade
  + UPT upgrade completed. Regression test pending.
  + UPT should be available on Prod (dependency)
  + caGrid 1.4 upgrade – on Hold.
* Other activities
  + Other maintenance and bug fixes.
  + TRANSCEND
    - Automatic caArray Refresh – Ongoing (CAINT-1115, CAINT-1116, CAINT-1117, CAINT-1118 were completed. The remaining subtasks for CAINT-1094 should be completed by the end if Iteration I18.)
    - Role based Permissions – Ongoing (CAINT-1107 being worked on in Iteration I17)
    - Single Sign-ON – Ongoing
    - TRANSCEND UAT on stage environment (Appscan ongoing)
* Project plan [https://ncisvn.nci.nih.gov/svn/caintegrator2/trunk/docs/project\_management/caintegrator\_project\_plan.mpp](https://ncisvn.nci.nih.gov/svn/caintegrator2/trunk/docs/project_management/caintegrator_project_plan.mpp" \t "_blank)

### TRANSCEND:

* caArray:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Key** | **Summary** | **Reporter** | **Fix Version/s** | **Status** | **UAT Release Date** |
| [TRANSCEND-67](https://tracker.nci.nih.gov/browse/TRANSCEND-67) | Permissions - Platform and Timepoint | Christina Warmington | Release 1 | Resolved | April |
| [TRANSCEND-106](https://tracker.nci.nih.gov/browse/TRANSCEND-106) | Enhanced Permissions - Treatment Arm | Eve Shalley | Release 1 | Resolved | April (depends on STAGE access by UCSF) |
| [TRANSCEND-80](https://tracker.nci.nih.gov/browse/TRANSCEND-80) | Single Sign-on Prototype | Kunal Modi | Release 1 | Resolved | N/A |
| [TRANSCEND-84](https://tracker.nci.nih.gov/browse/TRANSCEND-84) | caArray to provide capabilities to support Automatic Refresh of Sample Data | Kunal Modi | Release 1 | Resolved (integration tests pending) | May |
| [TRANSCEND-81](https://tracker.nci.nih.gov/browse/TRANSCEND-81) | Single Sign-on in caArray | Kunal Modi | Release 1 | In Progress | June |
| [TRANSCEND-40](https://tracker.nci.nih.gov/browse/TRANSCEND-40) | Audit Trail | Christina Warmington | Release 1 | In Progress | June |
|  |  |  |  |  |  |

* caIntegrator:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Key** | **Summary** | **Reporter** | **Fix Version/s** | **Status** | **UAT Release Date** |
| N/A | Study Versioning and Archiving | N/A | Release 1 | Resolved | April |
| [TRANSCEND-85](https://tracker.nci.nih.gov/browse/TRANSCEND-85) and [TRANSCEND-87](https://tracker.nci.nih.gov/browse/TRANSCEND-87) | Automatic Refresh | Kunal Modi | Release 1 | In Progress | May |
| [TRANSCEND-45](https://tracker.nci.nih.gov/browse/TRANSCEND-45) , [TRANSCEND-47](https://tracker.nci.nih.gov/browse/TRANSCEND-47) and [TRANSCEND-48](https://tracker.nci.nih.gov/browse/TRANSCEND-48) | Role Based Permissions | Eve-Shalley | Release 1 | In Progress | June |
| [TRANSCEND-79](https://tracker.nci.nih.gov/browse/TRANSCEND-79) | Single Sign-On | Kunal Modi | Release 1 | In Progress | June |

* Delivery:
  + caArray STAGE passed appscan and is now outside the firewall. Demo to UCSF is complete, and documentation is ready for UCSF to begin UAT.
  + Security appscan of caIntegrator (STAGE) is ongoing.
  + Both teams working on packaged delivery option (getting installer and documentation ready for UCSF) – targeted for May.
  + Our teams will review Kunal’s document to ensure that the hardware and software requirements being given to UCSF are correct.

### Systems and DBA:

* No updates this week.

### Documentation:

* No updates this week.

### Support and Knowledge Center:

* No updates this week.

## Open Action Items:

* Full list of closed and current action items are available here: <https://ncisvn.nci.nih.gov/svn/caarray2/trunk/docs/project_management/caArray_caIntegrator_Action_Items.xlsx>

| **Item #** | **Description** | **Responsible Party** | **Date Identified** | **Disposition** |
| --- | --- | --- | --- | --- |
| 40 | Check with Matt Kennedy and Eve re: getting hardware requirements to UCSF | Rashmi Srinivasa | 4/17/2012 | Complete |
| 41 | Check with Eve re: bringing back the risk related to unavailability of I-SPY2 data | Rashmi/Shine | 4/17/2012 | Not Started |